## 测试报告
停车场 | 测试日期 | 测试类型
深圳湾睿印VIP停车场 | 2024-10-16 | 摄像头检查
总数 | 3559相机 | 红绿灯相机
42 | 33 | 9
Pass | Fail | Untest
37 | 5 | 0
错误类型 | 数目
[相机]抽图失败（离线）-项目经理 | 2
[相机]相机严重被撞-交付经理 | 1
[相机]未生成debug图片-刘庆鑫 | 1
[相机]画面模糊-交付经理 | 1

## 测试结果
id | parking | parking_name | site_id | floor | cam_channel | cam_short | cam_ip | cam_type | lots | result | comment | resolve | case_assign | case_status | rgl_index | task_id | device | camera_img | debug_img | cam_lots | test_time | test_date | track_img
180215 | RAILIN_shenzhen_vip | 深圳湾睿印VIP停车场 | RAILIN_shenzhen_vip | B4F | ch03001 | 03-01 | 192.168.254.100 | rgl_cam | None | Pass |  |  |  |  | 0 | 165574ae-b36f-43fa-b9f9-f2ce989692da | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:43:75:48/1729042678_1.jpg | https://bj.bcebos.com/camera-manage/debug/RAILIN_shenzhen_vip/projection/03-01/cam_view_20241016094821.jpg | [{"floor": "B4F", "lot": "VIP011", "cam": "03-01"}] | 2024-10-16 09:37:58 | 2024-10-16 | None
180216 | RAILIN_shenzhen_vip | 深圳湾睿印VIP停车场 | RAILIN_shenzhen_vip | B4F | ch03002 | 03-02 | 192.168.254.101 | rgl_cam | None | Pass |  |  |  |  | 0 | 165574ae-b36f-43fa-b9f9-f2ce989692da | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:43:75:4f/1729042683_1.jpg | https://bj.bcebos.com/camera-manage/debug/RAILIN_shenzhen_vip/projection/03-02/cam_view_20241016094834.jpg | [{"floor": "B4F", "lot": "VIP014", "cam": "03-02"}, {"floor": "B4F", "lot": "VIP013", "cam": "03-02"}, {"floor": "B4F", "lot": "VIP012", "cam": "03-02"}] | 2024-10-16 09:38:03 | 2024-10-16 | None
180217 | RAILIN_shenzhen_vip | 深圳湾睿印VIP停车场 | RAILIN_shenzhen_vip | B4F | ch03003 | 03-03 | 192.168.254.102 | rgl_cam | None | Pass |  |  |  |  | 0 | 165574ae-b36f-43fa-b9f9-f2ce989692da | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:43:75:4d/1729042687_1.jpg | https://bj.bcebos.com/camera-manage/debug/RAILIN_shenzhen_vip/projection/03-03/cam_view_20241016094854.jpg | [{"floor": "B4F", "lot": "VIP015", "cam": "03-03"}] | 2024-10-16 09:38:06 | 2024-10-16 | None
180218 | RAILIN_shenzhen_vip | 深圳湾睿印VIP停车场 | RAILIN_shenzhen_vip | B4F | ch03004 | 03-04 | 192.168.254.103 | rgl_cam | None | Pass |  |  |  |  | 0 | 165574ae-b36f-43fa-b9f9-f2ce989692da | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:43:75:51/1729042689_1.jpg | https://bj.bcebos.com/camera-manage/debug/RAILIN_shenzhen_vip/projection/03-04/cam_view_20241016094912.jpg | [{"floor": "B4F", "lot": "VIP021", "cam": "03-04"}, {"floor": "B4F", "lot": "VIP020", "cam": "03-04"}] | 2024-10-16 09:38:09 | 2024-10-16 | None
180219 | RAILIN_shenzhen_vip | 深圳湾睿印VIP停车场 | RAILIN_shenzhen_vip | B4F | ch03005 | 03-05 | 192.168.254.104 | rgl_cam | None | Pass |  |  |  |  | 0 | 165574ae-b36f-43fa-b9f9-f2ce989692da | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:43:75:4c/1729042691_1.jpg | https://bj.bcebos.com/camera-manage/debug/RAILIN_shenzhen_vip/projection/03-05/cam_view_20241016094948.jpg | [{"floor": "B4F", "lot": "VIP019", "cam": "03-05"}, {"floor": "B4F", "lot": "VIP018", "cam": "03-05"}, {"floor": "B4F", "lot": "VIP017", "cam": "03-05"}, {"floor": "B4F", "lot": "VIP016", "cam": "03-05"}] | 2024-10-16 09:38:11 | 2024-10-16 | None
180220 | RAILIN_shenzhen_vip | 深圳湾睿印VIP停车场 | RAILIN_shenzhen_vip | B4F | ch03006 | 03-06 | 192.168.254.105 | rgl_cam | None | Pass |  |  |  |  | 0 | 165574ae-b36f-43fa-b9f9-f2ce989692da | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:43:75:42/1729042693_1.jpg | https://bj.bcebos.com/camera-manage/debug/RAILIN_shenzhen_vip/projection/03-06/cam_view_20241016095002.jpg | [{"floor": "B4F", "lot": "VIP010", "cam": "03-06"}] | 2024-10-16 09:38:13 | 2024-10-16 | None
180221 | RAILIN_shenzhen_vip | 深圳湾睿印VIP停车场 | RAILIN_shenzhen_vip | B4F | ch03007 | 03-07 | 192.168.254.106 | rgl_cam | None | Pass |  |  |  |  | 0 | 165574ae-b36f-43fa-b9f9-f2ce989692da | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:43:75:4e/1729042696_1.jpg | https://bj.bcebos.com/camera-manage/debug/RAILIN_shenzhen_vip/projection/03-07/cam_view_20241016095018.jpg | [{"floor": "B4F", "lot": "VIP009", "cam": "03-07"}, {"floor": "B4F", "lot": "VIP008", "cam": "03-07"}, {"floor": "B4F", "lot": "VIP007", "cam": "03-07"}] | 2024-10-16 09:38:15 | 2024-10-16 | None
180222 | RAILIN_shenzhen_vip | 深圳湾睿印VIP停车场 | RAILIN_shenzhen_vip | B4F | ch03008 | 03-08 | 192.168.254.107 | rgl_cam | None | Pass |  |  |  |  | 0 | 165574ae-b36f-43fa-b9f9-f2ce989692da | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:43:75:4b/1729042698_1.jpg | https://bj.bcebos.com/camera-manage/debug/RAILIN_shenzhen_vip/projection/03-08/cam_view_20241016095035.jpg | [{"floor": "B4F", "lot": "VIP006", "cam": "03-08"}, {"floor": "B4F", "lot": "VIP005", "cam": "03-08"}] | 2024-10-16 09:38:17 | 2024-10-16 | None
180223 | RAILIN_shenzhen_vip | 深圳湾睿印VIP停车场 | RAILIN_shenzhen_vip | B4F | ch03009 | 03-09 | 192.168.254.108 | rgl_cam | None | Pass |  |  |  |  | 0 | 165574ae-b36f-43fa-b9f9-f2ce989692da | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:43:75:45/1729042700_1.jpg | https://bj.bcebos.com/camera-manage/debug/RAILIN_shenzhen_vip/projection/03-09/cam_view_20241016095050.jpg | [{"floor": "B4F", "lot": "VIP004", "cam": "03-09"}, {"floor": "B4F", "lot": "VIP003", "cam": "03-09"}, {"floor": "B4F", "lot": "VIP002", "cam": "03-09"}, {"floor": "B4F", "lot": "VIP001", "cam": "03-09"}] | 2024-10-16 09:38:19 | 2024-10-16 | None
180224 | RAILIN_shenzhen_vip | 深圳湾睿印VIP停车场 | RAILIN_shenzhen_vip | B4F | ch01001 | 01-01 | 192.168.254.50 | 3559 | None | Pass |  |  |  |  | None | 165574ae-b36f-43fa-b9f9-f2ce989692da | 5236bc38f3603979fa748d75f374ea38 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/D4:E8:53:B0:73:51/20241016_093509.jpg | https://bj.bcebos.com/camera-manage/debug/RAILIN_shenzhen_vip/projection/01-01/cam_view_20241016093831.jpg | [] | 2024-10-16 09:35:08 | 2024-10-16 | None
180225 | RAILIN_shenzhen_vip | 深圳湾睿印VIP停车场 | RAILIN_shenzhen_vip | B4F | ch01002 | 01-02 | 192.168.254.51 | 3559 | None | Pass |  |  |  |  | None | 165574ae-b36f-43fa-b9f9-f2ce989692da | ac4f4bb82305a480def48ab5fa784c2e | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/D4:E8:53:B0:71:7C/20241016_093512.jpg | https://bj.bcebos.com/camera-manage/debug/RAILIN_shenzhen_vip/projection/01-02/cam_view_20241016093845.jpg | [] | 2024-10-16 09:35:11 | 2024-10-16 | None
180226 | RAILIN_shenzhen_vip | 深圳湾睿印VIP停车场 | RAILIN_shenzhen_vip | B4F | ch01003 | 01-03 | 192.168.254.52 | 3559 | None | Pass |  |  |  |  | None | 165574ae-b36f-43fa-b9f9-f2ce989692da | 60d6d56d0b30911a0e2905e8280b5234 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/D4:E8:53:B0:73:5C/20241016_093514.jpg | https://bj.bcebos.com/camera-manage/debug/RAILIN_shenzhen_vip/projection/01-03/cam_view_20241016093922.jpg | [] | 2024-10-16 09:35:14 | 2024-10-16 | None
180227 | RAILIN_shenzhen_vip | 深圳湾睿印VIP停车场 | RAILIN_shenzhen_vip | B4F | ch01004 | 01-04 | 192.168.254.53 | 3559 | None | Pass |  |  |  |  | None | 165574ae-b36f-43fa-b9f9-f2ce989692da | 06c76344537b8e34c388ee6dded01593 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/24:0F:9B:4B:7C:B4/20241016_093516.jpg | https://bj.bcebos.com/camera-manage/debug/RAILIN_shenzhen_vip/projection/01-04/cam_view_20241016093935.jpg | [] | 2024-10-16 09:35:16 | 2024-10-16 | None
180228 | RAILIN_shenzhen_vip | 深圳湾睿印VIP停车场 | RAILIN_shenzhen_vip | B4F | ch01005 | 01-05 | 192.168.254.54 | 3559 | None | Pass |  |  |  |  | None | 165574ae-b36f-43fa-b9f9-f2ce989692da | b5273d2a50021bc3b876f6ee4e458255 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/24:0F:9B:4B:7B:CA/20241016_093518.jpg | https://bj.bcebos.com/camera-manage/debug/RAILIN_shenzhen_vip/projection/01-05/cam_view_20241016093953.jpg | [] | 2024-10-16 09:35:18 | 2024-10-16 | None
180229 | RAILIN_shenzhen_vip | 深圳湾睿印VIP停车场 | RAILIN_shenzhen_vip | B4F | ch01006 | 01-06 | 192.168.254.55 | 3559 | None | Pass |  |  |  |  | None | 165574ae-b36f-43fa-b9f9-f2ce989692da | b86e36888dde0938a968f776feba6379 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/24:0F:9B:4B:7C:1F/20241016_093521.jpg | https://bj.bcebos.com/camera-manage/debug/RAILIN_shenzhen_vip/projection/01-06/cam_view_20241016094009.jpg | [] | 2024-10-16 09:35:21 | 2024-10-16 | None
180230 | RAILIN_shenzhen_vip | 深圳湾睿印VIP停车场 | RAILIN_shenzhen_vip | B4F | ch01007 | 01-07 | 192.168.254.56 | 3559 | None | Pass |  |  |  |  | None | 165574ae-b36f-43fa-b9f9-f2ce989692da | b6b3a8d98f7f55a9d54712ee95c30b61 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/24:0F:9B:4B:7B:64/20241016_093528.jpg | https://bj.bcebos.com/camera-manage/debug/RAILIN_shenzhen_vip/projection/01-07/cam_view_20241016094025.jpg | [] | 2024-10-16 09:35:28 | 2024-10-16 | None
180231 | RAILIN_shenzhen_vip | 深圳湾睿印VIP停车场 | RAILIN_shenzhen_vip | B4F | ch01008 | 01-08 | 192.168.254.57 | 3559 | None | Pass |  |  |  |  | None | 165574ae-b36f-43fa-b9f9-f2ce989692da | 948af884ac7dcd1374cf47f8f9b91180 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/24:0F:9B:4B:7B:F8/20241016_093530.jpg | https://bj.bcebos.com/camera-manage/debug/RAILIN_shenzhen_vip/projection/01-08/cam_view_20241016094039.jpg | [] | 2024-10-16 09:35:31 | 2024-10-16 | None
180232 | RAILIN_shenzhen_vip | 深圳湾睿印VIP停车场 | RAILIN_shenzhen_vip | B4F | ch01009 | 01-09 | 192.168.254.58 | 3559 | None | Pass |  |  |  |  | None | 165574ae-b36f-43fa-b9f9-f2ce989692da | 055e7cd0551667f6de22134bf9d10a8d | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/24:0F:9B:4B:7B:95/20241016_093533.jpg | https://bj.bcebos.com/camera-manage/debug/RAILIN_shenzhen_vip/projection/01-09/cam_view_20241016094052.jpg | [] | 2024-10-16 09:35:34 | 2024-10-16 | None
180233 | RAILIN_shenzhen_vip | 深圳湾睿印VIP停车场 | RAILIN_shenzhen_vip | B4F | ch01010 | 01-10 | 192.168.254.59 | 3559 | None | Pass |  |  |  |  | None | 165574ae-b36f-43fa-b9f9-f2ce989692da | a612febb7480990997da7fa6e29381b7 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/24:0F:9B:4B:7C:B1/20241016_093537.jpg | https://bj.bcebos.com/camera-manage/debug/RAILIN_shenzhen_vip/projection/01-10/cam_view_20241016094133.jpg | [] | 2024-10-16 09:35:37 | 2024-10-16 | None
180234 | RAILIN_shenzhen_vip | 深圳湾睿印VIP停车场 | RAILIN_shenzhen_vip | B4F | ch01011 | 01-11 | 192.168.254.60 | 3559 | None | Pass |  |  |  |  | None | 165574ae-b36f-43fa-b9f9-f2ce989692da | 0f259009a3cf6b70d2e400c4ccbd4c3d | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/24:0F:9B:4B:7B:7A/20241016_093541.jpg | https://bj.bcebos.com/camera-manage/debug/RAILIN_shenzhen_vip/projection/01-11/cam_view_20241016094145.jpg | [] | 2024-10-16 09:35:41 | 2024-10-16 | None
180235 | RAILIN_shenzhen_vip | 深圳湾睿印VIP停车场 | RAILIN_shenzhen_vip | B4F | ch01012 | 01-12 | 192.168.254.61 | 3559 | None | Pass |  |  |  |  | None | 165574ae-b36f-43fa-b9f9-f2ce989692da | 1765d8a27f8e51af99cf7e0c677f518d | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/D4:E8:53:B0:73:71/20241016_093543.jpg | https://bj.bcebos.com/camera-manage/debug/RAILIN_shenzhen_vip/projection/01-12/cam_view_20241016094157.jpg | [] | 2024-10-16 09:35:44 | 2024-10-16 | None
180236 | RAILIN_shenzhen_vip | 深圳湾睿印VIP停车场 | RAILIN_shenzhen_vip | B4F | ch01013 | 01-13 | 192.168.254.62 | 3559 | None | Pass |  |  |  |  | None | 165574ae-b36f-43fa-b9f9-f2ce989692da | 9047ccc8a2366cf390b6614800c74738 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/D4:E8:53:B0:73:59/20241016_093544.jpg | https://bj.bcebos.com/camera-manage/debug/RAILIN_shenzhen_vip/projection/01-13/cam_view_20241016094211.jpg | [] | 2024-10-16 09:35:46 | 2024-10-16 | None
180237 | RAILIN_shenzhen_vip | 深圳湾睿印VIP停车场 | RAILIN_shenzhen_vip | B4F | ch01014 | 01-14 | 192.168.254.63 | 3559 | None | Pass |  |  |  |  | None | 165574ae-b36f-43fa-b9f9-f2ce989692da | b6ba5fe45d0509f3a6f26afb0fd6648b | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/D4:E8:53:B0:71:6C/20241016_093548.jpg | https://bj.bcebos.com/camera-manage/debug/RAILIN_shenzhen_vip/projection/01-14/cam_view_20241016094227.jpg | [] | 2024-10-16 09:35:50 | 2024-10-16 | None
180238 | RAILIN_shenzhen_vip | 深圳湾睿印VIP停车场 | RAILIN_shenzhen_vip | B4F | ch01015 | 01-15 | 192.168.254.64 | 3559 | None | Pass |  |  |  |  | None | 165574ae-b36f-43fa-b9f9-f2ce989692da | fccc5f3d8eb5dac6f36efe2f4cb9371b | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/D4:E8:53:B0:73:78/20241016_093551.jpg | https://bj.bcebos.com/camera-manage/debug/RAILIN_shenzhen_vip/projection/01-15/cam_view_20241016094241.jpg | [] | 2024-10-16 09:35:52 | 2024-10-16 | None
180239 | RAILIN_shenzhen_vip | 深圳湾睿印VIP停车场 | RAILIN_shenzhen_vip | B4F | ch01016 | 01-16 | 192.168.254.65 | 3559 | None | Pass |  |  |  |  | None | 165574ae-b36f-43fa-b9f9-f2ce989692da | 578c3b7997d66c939c558fca46374dfb | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/D4:E8:53:B0:72:5E/20241016_093553.jpg | https://bj.bcebos.com/camera-manage/debug/RAILIN_shenzhen_vip/projection/01-16/cam_view_20241016094300.jpg | [] | 2024-10-16 09:35:54 | 2024-10-16 | None
180240 | RAILIN_shenzhen_vip | 深圳湾睿印VIP停车场 | RAILIN_shenzhen_vip | B4F | ch01017 | 01-17 | 192.168.254.66 | 3559 | None | Pass |  |  |  |  | None | 165574ae-b36f-43fa-b9f9-f2ce989692da | 206d9b58421edf1b611b020a94ccb36a | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/D4:E8:53:B0:73:5A/20241016_093556.jpg | https://bj.bcebos.com/camera-manage/debug/RAILIN_shenzhen_vip/projection/01-17/cam_view_20241016094314.jpg | [] | 2024-10-16 09:35:56 | 2024-10-16 | None
180241 | RAILIN_shenzhen_vip | 深圳湾睿印VIP停车场 | RAILIN_shenzhen_vip | B4F | ch01018 | 01-18 | 192.168.254.67 | 3559 | None | Pass |  |  |  |  | None | 165574ae-b36f-43fa-b9f9-f2ce989692da | 6b125c26f3ee4d95d3603f73d8514856 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/D4:E8:53:53:09:7F/20241016_093559.jpg | https://bj.bcebos.com/camera-manage/debug/RAILIN_shenzhen_vip/projection/01-18/cam_view_20241016094328.jpg | [] | 2024-10-16 09:35:58 | 2024-10-16 | None
180242 | RAILIN_shenzhen_vip | 深圳湾睿印VIP停车场 | RAILIN_shenzhen_vip | B4F | ch01019 | 01-19 | 192.168.254.68 | 3559 | None | Pass |  |  |  |  | None | 165574ae-b36f-43fa-b9f9-f2ce989692da | c8caef317595b6cbb1392c75b85e907b | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/D4:E8:53:53:09:80/20241016_093602.jpg | https://bj.bcebos.com/camera-manage/debug/RAILIN_shenzhen_vip/projection/01-19/cam_view_20241016094410.jpg | [] | 2024-10-16 09:36:03 | 2024-10-16 | None
180243 | RAILIN_shenzhen_vip | 深圳湾睿印VIP停车场 | RAILIN_shenzhen_vip | B4F | ch01020 | 01-20 | 192.168.254.69 | 3559 | None | Pass |  |  |  |  | None | 165574ae-b36f-43fa-b9f9-f2ce989692da | f1dd5ab96bf399f27a6b83a804cae12a | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/D4:E8:53:53:09:83/20241016_093609.jpg | https://bj.bcebos.com/camera-manage/debug/RAILIN_shenzhen_vip/projection/01-20/cam_view_20241016094429.jpg | [] | 2024-10-16 09:36:10 | 2024-10-16 | None
180244 | RAILIN_shenzhen_vip | 深圳湾睿印VIP停车场 | RAILIN_shenzhen_vip | B3F | ch02001 | 02-01 | 192.168.254.70 | 3559 | None | Pass |  |  |  |  | None | 165574ae-b36f-43fa-b9f9-f2ce989692da | ad0664887c41385eff37521b23c7a4f2 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/D4:E8:53:B0:73:46/20241016_093614.jpg | https://bj.bcebos.com/camera-manage/debug/RAILIN_shenzhen_vip/projection/02-01/cam_view_20241016094446.jpg | [] | 2024-10-16 09:36:13 | 2024-10-16 | None
180245 | RAILIN_shenzhen_vip | 深圳湾睿印VIP停车场 | RAILIN_shenzhen_vip | B3F | ch02002 | 02-02 | 192.168.254.71 | 3559 | None | Pass |  |  |  |  | None | 165574ae-b36f-43fa-b9f9-f2ce989692da | 97ff6ca658bb5c66b230c8adc25ac57d | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/D4:E8:53:B0:73:40/20241016_093617.jpg | https://bj.bcebos.com/camera-manage/debug/RAILIN_shenzhen_vip/projection/02-02/cam_view_20241016094458.jpg | [] | 2024-10-16 09:36:16 | 2024-10-16 | None
180246 | RAILIN_shenzhen_vip | 深圳湾睿印VIP停车场 | RAILIN_shenzhen_vip | B3F | ch02003 | 02-03 | 192.168.254.72 | 3559 | None | Fail |  |  | [相机]抽图失败（离线）-项目经理 |  | None | 165574ae-b36f-43fa-b9f9-f2ce989692da | 2cf2eda43e0089edeb13e732ccd0144f | N | http://180.76.166.204:8087/other/no_debug.png | [] | 2024-10-16 11:12:12 | 2024-10-16 | None
180247 | RAILIN_shenzhen_vip | 深圳湾睿印VIP停车场 | RAILIN_shenzhen_vip | B3F | ch02004 | 02-04 | 192.168.254.73 | 3559 | None | Pass |  |  |  |  | None | 165574ae-b36f-43fa-b9f9-f2ce989692da | c42778cdd264264b46604992d09117b5 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/D4:E8:53:B0:71:77/20241016_093655.jpg | https://bj.bcebos.com/camera-manage/debug/RAILIN_shenzhen_vip/projection/02-04/cam_view_20241016094547.jpg | [] | 2024-10-16 09:36:54 | 2024-10-16 | None
180248 | RAILIN_shenzhen_vip | 深圳湾睿印VIP停车场 | RAILIN_shenzhen_vip | B3F | ch02005 | 02-05 | 192.168.254.74 | 3559 | None | Pass |  |  |  |  | None | 165574ae-b36f-43fa-b9f9-f2ce989692da | eb791d988045e38e14631deee76979d7 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/D4:E8:53:B0:71:F7/20241016_093657.jpg | https://bj.bcebos.com/camera-manage/debug/RAILIN_shenzhen_vip/projection/02-05/cam_view_20241016094623.jpg | [] | 2024-10-16 09:36:57 | 2024-10-16 | None
180249 | RAILIN_shenzhen_vip | 深圳湾睿印VIP停车场 | RAILIN_shenzhen_vip | B3F | ch02006 | 02-06 | 192.168.254.75 | 3559 | None | Fail |  |  | [相机]相机严重被撞-交付经理 |  | None | 165574ae-b36f-43fa-b9f9-f2ce989692da | 373c65f0a72df62b8eb8426e322b30cf | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/D4:E8:53:B0:72:22/20241016_093659.jpg | https://bj.bcebos.com/camera-manage/debug/RAILIN_shenzhen_vip/projection/02-06/cam_view_20241016094636.jpg | [] | 2024-10-16 09:36:59 | 2024-10-16 | None
180250 | RAILIN_shenzhen_vip | 深圳湾睿印VIP停车场 | RAILIN_shenzhen_vip | B3F | ch02007 | 02-07 | 192.168.254.76 | 3559 | None | Pass |  |  |  |  | None | 165574ae-b36f-43fa-b9f9-f2ce989692da | 67c2cb6831587bffbd345554ed4b3a7b | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/D4:E8:53:B0:72:8A/20241016_093702.jpg | https://bj.bcebos.com/camera-manage/debug/RAILIN_shenzhen_vip/projection/02-07/cam_view_20241016094652.jpg | [] | 2024-10-16 09:37:01 | 2024-10-16 | None
180251 | RAILIN_shenzhen_vip | 深圳湾睿印VIP停车场 | RAILIN_shenzhen_vip | B3F | ch02008 | 02-08 | 192.168.254.77 | 3559 | None | Pass |  |  |  |  | None | 165574ae-b36f-43fa-b9f9-f2ce989692da | 782a1c316ae63c2913d76949dd589feb | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/D4:E8:53:B0:73:55/20241016_093704.jpg | https://bj.bcebos.com/camera-manage/debug/RAILIN_shenzhen_vip/projection/02-08/cam_view_20241016094713.jpg | [] | 2024-10-16 09:37:04 | 2024-10-16 | None
180252 | RAILIN_shenzhen_vip | 深圳湾睿印VIP停车场 | RAILIN_shenzhen_vip | B3F | ch02009 | 02-09 | 192.168.254.78 | 3559 | None | Fail |  |  | [相机]未生成debug图片-刘庆鑫 |  | None | 165574ae-b36f-43fa-b9f9-f2ce989692da | d3b2d93a3a65b6f275c773b6d90197ec | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/D4:E8:53:B0:72:E5/20241016_093708.jpg | http://180.76.166.204:8087/other/no_debug.png | [] | 2024-10-16 09:37:07 | 2024-10-16 | None
180253 | RAILIN_shenzhen_vip | 深圳湾睿印VIP停车场 | RAILIN_shenzhen_vip | B3F | ch02010 | 02-10 | 192.168.254.79 | 3559 | None | Fail |  |  | [相机]抽图失败（离线）-项目经理 |  | None | 165574ae-b36f-43fa-b9f9-f2ce989692da | 3927b39a46e2b4266b9e9ff3439ac379 | N | http://180.76.166.204:8087/other/no_debug.png | [] | 2024-10-16 11:12:44 | 2024-10-16 | None
180254 | RAILIN_shenzhen_vip | 深圳湾睿印VIP停车场 | RAILIN_shenzhen_vip | B3F | ch02011 | 02-11 | 192.168.254.80 | 3559 | None | Fail |  |  | [相机]画面模糊-交付经理 |  | None | 165574ae-b36f-43fa-b9f9-f2ce989692da | 6d01a905337866a5cb82c5bfde004b6a | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/D4:E8:53:B0:72:9A/20241016_093738.jpg | https://bj.bcebos.com/camera-manage/debug/RAILIN_shenzhen_vip/projection/02-11/cam_view_20241016094730.jpg | [] | 2024-10-16 09:37:38 | 2024-10-16 | None
180255 | RAILIN_shenzhen_vip | 深圳湾睿印VIP停车场 | RAILIN_shenzhen_vip | B4F | ch02012 | 02-12 | 192.168.254.81 | 3559 | None | Pass |  |  |  |  | None | 165574ae-b36f-43fa-b9f9-f2ce989692da | bce5c096671c4ad193f33fd8758f9447 | https://move-pic-service.su.bcebos.com/45ab40ba-1a01-4945-8aac-9754c1b0b8b8.jpg | https://bj.bcebos.com/camera-manage/debug/RAILIN_shenzhen_vip/projection/02-12/cam_view_20241016094748.jpg | [] | 2024-10-16 09:37:43 | 2024-10-16 | None
180256 | RAILIN_shenzhen_vip | 深圳湾睿印VIP停车场 | RAILIN_shenzhen_vip | B4F | ch02013 | 02-13 | 192.168.254.82 | 3559 | None | Pass |  |  |  |  | None | 165574ae-b36f-43fa-b9f9-f2ce989692da | b57ee35ca26cc3e7a10190a058613842 | https://move-pic-service.su.bcebos.com/4ef60bc9-f76a-4888-b2da-4ac05c81bd98.jpg | https://bj.bcebos.com/camera-manage/debug/RAILIN_shenzhen_vip/projection/02-13/cam_view_20241016094805.jpg | [] | 2024-10-16 09:37:51 | 2024-10-16 | None