## 测试报告
停车场 | 测试日期 | 测试类型
克拉玛依汇嘉滨河广场停车场 | 2024-10-10 | 摄像头检查
总数 | 3559相机 | 红绿灯相机
114 | 25 | 89
Pass | Fail | Untest
110 | 4 | 0
错误类型 | 数目
[相机]画面被遮挡--交付经理 | 2
[相机]相机轻微移动，车位投影线和实际车位线误差10%~30%-天津标定 | 1
[相机]相机严重被撞-交付经理 | 1

## 测试结果
id | parking | parking_name | site_id | floor | cam_channel | cam_short | cam_ip | cam_type | lots | result | comment | resolve | case_assign | case_status | rgl_index | task_id | device | camera_img | debug_img | cam_lots | test_time | test_date
176508 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch01001 | 01-01 | 192.42.222.1 | 3559 | None | Fail |  |  | [相机]相机轻微移动，车位投影线和实际车位线误差10%~30%-天津标定 |  | None | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | bc3706c757dd097d8e228f7fb5a43936 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/2C:A5:9C:09:8A:4C/20241008_185859.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/01-01/cam_view_20241008190511.jpg | [] | 2024-10-08 18:58:58 | 2024-10-08
176509 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch01010 | 01-10 | 192.42.222.10 | 3559 | None | Pass |  |  |  |  | None | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | 3da16a6416b142b1b02b941708a4337b | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/EC:C8:9C:76:B5:EF/20241008_185922.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/01-10/cam_view_20241008190728.jpg | [] | 2024-10-08 18:59:22 | 2024-10-08
176510 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03058 | 03-58 | 192.42.222.100 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:43:b4:00/1728529931_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-58/cam_view_20241010111223.jpg | [{"floor": "B1F", "lot": "B-118", "cam": "03-58"}, {"floor": "B1F", "lot": "B-117", "cam": "03-58"}, {"floor": "B1F", "lot": "B-116", "cam": "03-58"}] | 2024-10-10 11:12:11 | 2024-10-10
176511 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03084 | 03-84 | 192.42.222.100 | rgl_cam | None | Pass |  |  |  |  | 1 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:43:b4:00/1728385476_2.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-84/cam_view_20241008194553.jpg | [{"floor": "B1F", "lot": "B-121", "cam": "03-84"}, {"floor": "B1F", "lot": "B-120", "cam": "03-84"}, {"floor": "B1F", "lot": "B-119", "cam": "03-84"}] | 2024-10-08 19:04:36 | 2024-10-08
176512 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03059 | 03-59 | 192.42.222.101 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:43:b4:03/1728385399_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-59/cam_view_20241008193452.jpg | [{"floor": "B1F", "lot": "B-225", "cam": "03-59"}, {"floor": "B1F", "lot": "B-224", "cam": "03-59"}] | 2024-10-08 19:03:19 | 2024-10-08
176513 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03085 | 03-85 | 192.42.222.101 | rgl_cam | None | Pass |  |  |  |  | 1 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:43:b4:03/1728385479_2.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-85/cam_view_20241008194621.jpg | [{"floor": "B1F", "lot": "B-231", "cam": "03-85"}, {"floor": "B1F", "lot": "B-230", "cam": "03-85"}, {"floor": "B1F", "lot": "B-229", "cam": "03-85"}] | 2024-10-08 19:04:39 | 2024-10-08
176514 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03060 | 03-60 | 192.42.222.102 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:43:b3:fd/1728385403_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-60/cam_view_20241008193525.jpg | [{"floor": "B1F", "lot": "B-228", "cam": "03-60"}, {"floor": "B1F", "lot": "B-227", "cam": "03-60"}] | 2024-10-08 19:03:22 | 2024-10-08
176515 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03086 | 03-86 | 192.42.222.102 | rgl_cam | None | Pass |  |  |  |  | 1 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:43:b3:fd/1728385482_2.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-86/cam_view_20241008194653.jpg | [{"floor": "B1F", "lot": "B-223", "cam": "03-86"}, {"floor": "B1F", "lot": "B-222", "cam": "03-86"}] | 2024-10-08 19:04:42 | 2024-10-08
176516 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03037 | 03-37 | 192.42.222.103 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9b:60/1728385332_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-37/cam_view_20241008192510.jpg | [{"floor": "B1F", "lot": "B-079", "cam": "03-37"}, {"floor": "B1F", "lot": "B-078", "cam": "03-37"}, {"floor": "B1F", "lot": "B-077", "cam": "03-37"}] | 2024-10-08 19:02:12 | 2024-10-08
176517 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03038 | 03-38 | 192.42.222.104 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9b:4f/1728385334_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-38/cam_view_20241008192527.jpg | [{"floor": "B1F", "lot": "A-046", "cam": "03-38"}, {"floor": "B1F", "lot": "A-045", "cam": "03-38"}, {"floor": "B1F", "lot": "A-044", "cam": "03-38"}] | 2024-10-08 19:02:14 | 2024-10-08
176518 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch01011 | 01-11 | 192.42.222.11 | 3559 | None | Pass |  |  |  |  | None | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | 43244b13c0915e52a23fa78fa69d3e5f | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/ec%3Ac8%3A9c%3A76%3Ab3%3Af7/20241008_185925.jpg?AWSAccessKeyId=LTAI4FoVSLV5bUhjS5nrUdGG&Signature=8J3GuiD7FOVdiOZq2JeXYq8HStg%3D&Expires=3305185166 | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/01-11/cam_view_20241008190747.jpg | [] | 2024-10-08 18:59:25 | 2024-10-08
176519 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch01012 | 01-12 | 192.42.222.12 | 3559 | None | Pass |  |  |  |  | None | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | 3403b487729eebc25a0a22c5a1e177c1 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/ec%3Ac8%3A9c%3A76%3Ab5%3Ab7/20241008_185928.jpg?AWSAccessKeyId=LTAI4FoVSLV5bUhjS5nrUdGG&Signature=Q7q%2FY9TAtc8RAD02B3W%2FJi6%2F%2Bn0%3D&Expires=3305185169 | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/01-12/cam_view_20241008190813.jpg | [] | 2024-10-08 18:59:27 | 2024-10-08
176520 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch01013 | 01-13 | 192.42.222.13 | 3559 | None | Pass |  |  |  |  | None | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | a166ab191857add557070699bac0cfc1 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/ec%3Ac8%3A9c%3A76%3Ab6%3A7a/20241008_185932.jpg?AWSAccessKeyId=LTAI4FoVSLV5bUhjS5nrUdGG&Signature=rCBDr7vvTwrEQl1gFZlzYAcDUvs%3D&Expires=3305185172 | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/01-13/cam_view_20241008190829.jpg | [] | 2024-10-08 18:59:30 | 2024-10-08
176521 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch01014 | 01-14 | 192.42.222.14 | 3559 | None | Pass |  |  |  |  | None | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | a8998f85f556df18146b45ebc26b58f0 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/ec%3Ac8%3A9c%3A76%3Ab5%3A5b/20241008_185934.jpg?AWSAccessKeyId=LTAI4FoVSLV5bUhjS5nrUdGG&Signature=qmS4XF4sEfS4lhkRnJfzybEitP0%3D&Expires=3305185175 | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/01-14/cam_view_20241008190844.jpg | [] | 2024-10-08 18:59:33 | 2024-10-08
176522 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch01015 | 01-15 | 192.42.222.15 | 3559 | None | Fail |  |  | [相机]相机严重被撞-交付经理 |  | None | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | 9a89049cd388ac2c92132a1c50288fa9 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/ec%3Ac8%3A9c%3A76%3Ab5%3A48/20241008_185936.jpg?AWSAccessKeyId=LTAI4FoVSLV5bUhjS5nrUdGG&Signature=nfeh9LtvfEx5Q3UyQeDASYNkQTQ%3D&Expires=3305185177 | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/01-15/cam_view_20241008190859.jpg | [] | 2024-10-08 18:59:35 | 2024-10-08
176523 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch01016 | 01-16 | 192.42.222.16 | 3559 | None | Pass |  |  |  |  | None | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | 21c53cc44d20c0a927b7f4411376ccd7 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/EC:C8:9C:76:B5:F4/20241008_185938.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/01-16/cam_view_20241008190918.jpg | [] | 2024-10-08 18:59:38 | 2024-10-08
176524 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch01017 | 01-17 | 192.42.222.17 | 3559 | None | Pass |  |  |  |  | None | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | 21db90b3fa6f5f909807a2f7f4cd5486 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/EC:C8:9C:76:B5:B1/20241008_185941.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/01-17/cam_view_20241008190937.jpg | [{"floor": "B1F", "lot": "A-031", "cam": "01-17"}] | 2024-10-08 18:59:41 | 2024-10-08
176525 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch01018 | 01-18 | 192.42.222.18 | 3559 | None | Pass |  |  |  |  | None | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | d4e73d05d63394f263f8986fc1114627 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/2C:A5:9C:09:8B:84/20241008_185944.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/01-18/cam_view_20241008190953.jpg | [] | 2024-10-08 18:59:43 | 2024-10-08
176526 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch01019 | 01-19 | 192.42.222.19 | 3559 | None | Pass |  |  |  |  | None | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | 7bd6c737ee79b638504c8bac1f73387e | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/2C:A5:9C:09:8B:1B/20241008_185947.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/01-19/cam_view_20241008191016.jpg | [{"floor": "B1F", "lot": "A-167", "cam": "01-19"}, {"floor": "B1F", "lot": "A-166", "cam": "01-19"}, {"floor": "B1F", "lot": "A-165", "cam": "01-19"}, {"floor": "B1F", "lot": "A-164", "cam": "01-19"}, {"floor": "B1F", "lot": "A-163", "cam": "01-19"}, {"floor": "B1F", "lot": "A-162", "cam": "01-19"}] | 2024-10-08 18:59:46 | 2024-10-08
176527 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch01002 | 01-02 | 192.42.222.2 | 3559 | None | Pass |  |  |  |  | None | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | 724ece3bcaf80f10e7a1d643b932920d | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/2C:A5:9C:09:95:2A/20241008_185902.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/01-02/cam_view_20241008190526.jpg | [] | 2024-10-08 18:59:01 | 2024-10-08
176528 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch01020 | 01-20 | 192.42.222.20 | 3559 | None | Pass |  |  |  |  | None | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | 967bdceb67b75e13d52cd074c0b7b561 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/2C:A5:9C:09:8A:B3/20241008_185949.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/01-20/cam_view_20241008191031.jpg | [] | 2024-10-08 18:59:48 | 2024-10-08
176529 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch01021 | 01-21 | 192.42.222.21 | 3559 | None | Pass |  |  |  |  | None | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | 1f9bea4aa389172d7679d7969a54a7a3 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/2C:A5:9C:09:8A:9F/20241010_113025.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/01-21/cam_view_20241010113033.jpg | [] | 2024-10-10 11:30:24 | 2024-10-10
176530 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch01022 | 01-22 | 192.42.222.22 | 3559 | None | Pass |  |  |  |  | None | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | bbd25315ffa4529c94c83b32a30def94 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/2C:A5:9C:09:8C:3F/20241008_190035.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/01-22/cam_view_20241008191126.jpg | [] | 2024-10-08 19:00:34 | 2024-10-08
176531 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch01023 | 01-23 | 192.42.222.23 | 3559 | None | Pass |  |  |  |  | None | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | 8b992f5d3a3390db337863dc6a9692ac | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/2C:A5:9C:09:8C:43/20241008_190037.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/01-23/cam_view_20241008191142.jpg | [] | 2024-10-08 19:00:37 | 2024-10-08
176532 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch01024 | 01-24 | 192.42.222.24 | 3559 | None | Pass |  |  |  |  | None | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | 02d1ea06628a35733fde7bb41f57598d | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/2C:A5:9C:09:8B:78/20241008_190040.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/01-24/cam_view_20241008191158.jpg | [] | 2024-10-08 19:00:39 | 2024-10-08
176533 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch01025 | 01-25 | 192.42.222.25 | 3559 | None | Pass |  |  |  |  | None | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | 2dede12fe6de90a9a56f83c57497a556 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/2C:A5:9C:09:8A:87/20241008_190042.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/01-25/cam_view_20241008191217.jpg | [] | 2024-10-08 19:00:41 | 2024-10-08
176534 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch01003 | 01-03 | 192.42.222.3 | 3559 | None | Pass |  |  |  |  | None | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | 4c10a0cacd6a45dbf1e4fac1d2294ada | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/2C:A5:9C:09:95:D3/20241008_185904.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/01-03/cam_view_20241008190543.jpg | [] | 2024-10-08 18:59:04 | 2024-10-08
176535 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch01004 | 01-04 | 192.42.222.4 | 3559 | None | Pass |  |  |  |  | None | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | 6f6785c02b98c40e954c7ab3b0c34398 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/2C:A5:9C:09:94:5B/20241008_185907.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/01-04/cam_view_20241008190556.jpg | [] | 2024-10-08 18:59:06 | 2024-10-08
176536 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03001 | 03-01 | 192.42.222.41 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:dd/1728385245_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-01/cam_view_20241008191232.jpg | [{"floor": "B1F", "lot": "A-211", "cam": "03-01"}, {"floor": "B1F", "lot": "A-210", "cam": "03-01"}, {"floor": "B1F", "lot": "A-209", "cam": "03-01"}] | 2024-10-08 19:00:44 | 2024-10-08
176537 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03002 | 03-02 | 192.42.222.42 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:e3/1728385248_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-02/cam_view_20241008191246.jpg | [{"floor": "B1F", "lot": "A-185", "cam": "03-02"}, {"floor": "B1F", "lot": "A-184", "cam": "03-02"}, {"floor": "B1F", "lot": "A-183", "cam": "03-02"}] | 2024-10-08 19:00:47 | 2024-10-08
176538 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03003 | 03-03 | 192.42.222.43 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:e0/1728385249_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-03/cam_view_20241008191259.jpg | [{"floor": "B1F", "lot": "A-294", "cam": "03-03"}, {"floor": "B1F", "lot": "A-293", "cam": "03-03"}] | 2024-10-08 19:00:49 | 2024-10-08
176539 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03004 | 03-04 | 192.42.222.44 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:d4/1728385251_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-04/cam_view_20241008191314.jpg | [{"floor": "B1F", "lot": "A-182", "cam": "03-04"}, {"floor": "B1F", "lot": "A-181", "cam": "03-04"}, {"floor": "B1F", "lot": "A-180", "cam": "03-04"}] | 2024-10-08 19:00:51 | 2024-10-08
176540 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03005 | 03-05 | 192.42.222.45 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:db/1728385253_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-05/cam_view_20241008191328.jpg | [{"floor": "B1F", "lot": "A-208", "cam": "03-05"}, {"floor": "B1F", "lot": "A-207", "cam": "03-05"}, {"floor": "B1F", "lot": "A-206", "cam": "03-05"}] | 2024-10-08 19:00:52 | 2024-10-08
176541 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03006 | 03-06 | 192.42.222.46 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:d2/1728385255_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-06/cam_view_20241008191357.jpg | [{"floor": "B1F", "lot": "A-036", "cam": "03-06"}, {"floor": "B1F", "lot": "A-035", "cam": "03-06"}, {"floor": "B1F", "lot": "A-034", "cam": "03-06"}] | 2024-10-08 19:00:54 | 2024-10-08
176542 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03007 | 03-07 | 192.42.222.47 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:e7/1728385256_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-07/cam_view_20241008191421.jpg | [{"floor": "B1F", "lot": "A-055", "cam": "03-07"}, {"floor": "B1F", "lot": "A-054", "cam": "03-07"}, {"floor": "B1F", "lot": "A-053", "cam": "03-07"}] | 2024-10-08 19:00:56 | 2024-10-08
176543 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03008 | 03-08 | 192.42.222.48 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:43:b4:02/1728385258_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-08/cam_view_20241008191442.jpg | [{"floor": "B1F", "lot": "A-067", "cam": "03-08"}, {"floor": "B1F", "lot": "A-066", "cam": "03-08"}, {"floor": "B1F", "lot": "A-065", "cam": "03-08"}] | 2024-10-08 19:00:57 | 2024-10-08
176544 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03091 | 03-91 | 192.42.222.48 | rgl_cam | None | Pass |  |  |  |  | 1 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:43:b4:02/1728385496_2.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-91/cam_view_20241008194825.jpg | [] | 2024-10-08 19:04:56 | 2024-10-08
176545 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch01005 | 01-05 | 192.42.222.5 | 3559 | None | Pass |  |  |  |  | None | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | fb702b970a3b36458782494f3812f0f8 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/2C:A5:9C:09:95:A0/20241008_185910.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/01-05/cam_view_20241008190610.jpg | [{"floor": "B1F", "lot": "A-191", "cam": "01-05"}, {"floor": "B1F", "lot": "A-190", "cam": "01-05"}, {"floor": "B1F", "lot": "A-189", "cam": "01-05"}] | 2024-10-08 18:59:09 | 2024-10-08
176546 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03062 | 03-62 | 192.42.222.50 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:43:b4:04/1728385407_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-62/cam_view_20241008193546.jpg | [{"floor": "B1F", "lot": "A-058", "cam": "03-62"}, {"floor": "B1F", "lot": "A-057", "cam": "03-62"}, {"floor": "B1F", "lot": "A-056", "cam": "03-62"}] | 2024-10-08 19:03:26 | 2024-10-08
176547 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03088 | 03-88 | 192.42.222.50 | rgl_cam | None | Pass |  |  |  |  | 1 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:43:b4:04/1728385486_2.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-88/cam_view_20241008194729.jpg | [] | 2024-10-08 19:04:46 | 2024-10-08
176548 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03063 | 03-63 | 192.42.222.51 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:43:b3:ff/1728385409_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-63/cam_view_20241008193604.jpg | [{"floor": "B1F", "lot": "A-052", "cam": "03-63"}, {"floor": "B1F", "lot": "A-051", "cam": "03-63"}, {"floor": "B1F", "lot": "A-050", "cam": "03-63"}] | 2024-10-08 19:03:29 | 2024-10-08
176549 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03089 | 03-89 | 192.42.222.51 | rgl_cam | None | Pass |  |  |  |  | 1 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:43:b3:ff/1728385489_2.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-89/cam_view_20241008194749.jpg | [{"floor": "B1F", "lot": "A-042", "cam": "03-89"}, {"floor": "B1F", "lot": "A-041", "cam": "03-89"}, {"floor": "B1F", "lot": "A-040", "cam": "03-89"}] | 2024-10-08 19:04:48 | 2024-10-08
176550 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03064 | 03-64 | 192.42.222.52 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:43:b3:f8/1728385412_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-64/cam_view_20241008193628.jpg | [{"floor": "B1F", "lot": "B-070", "cam": "03-64"}, {"floor": "B1F", "lot": "B-069", "cam": "03-64"}, {"floor": "B1F", "lot": "B-068", "cam": "03-64"}] | 2024-10-08 19:03:32 | 2024-10-08
176551 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03090 | 03-90 | 192.42.222.52 | rgl_cam | None | Pass |  |  |  |  | 1 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:43:b3:f8/1728385492_2.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-90/cam_view_20241008194807.jpg | [] | 2024-10-08 19:04:52 | 2024-10-08
176552 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03009 | 03-09 | 192.42.222.53 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:46:88:5b/1728385261_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-09/cam_view_20241008191457.jpg | [{"floor": "B1F", "lot": "B-073", "cam": "03-09"}, {"floor": "B1F", "lot": "B-072", "cam": "03-09"}, {"floor": "B1F", "lot": "B-071", "cam": "03-09"}] | 2024-10-08 19:01:00 | 2024-10-08
176553 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03010 | 03-10 | 192.42.222.54 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:46:88:5e/1728385264_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-10/cam_view_20241008191527.jpg | [{"floor": "B1F", "lot": "B-076", "cam": "03-10"}, {"floor": "B1F", "lot": "B-075", "cam": "03-10"}, {"floor": "B1F", "lot": "B-074", "cam": "03-10"}] | 2024-10-08 19:01:03 | 2024-10-08
176554 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03011 | 03-11 | 192.42.222.55 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:46:88:66/1728385267_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-11/cam_view_20241008191543.jpg | [{"floor": "B1F", "lot": "B-107", "cam": "03-11"}, {"floor": "B1F", "lot": "B-106", "cam": "03-11"}] | 2024-10-08 19:01:06 | 2024-10-08
176555 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03012 | 03-12 | 192.42.222.56 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:46:88:62/1728385269_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-12/cam_view_20241008191556.jpg | [{"floor": "B1F", "lot": "B-109", "cam": "03-12"}, {"floor": "B1F", "lot": "B-108", "cam": "03-12"}] | 2024-10-08 19:01:09 | 2024-10-08
176556 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03013 | 03-13 | 192.42.222.57 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:e4/1728385272_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-13/cam_view_20241008191615.jpg | [{"floor": "B1F", "lot": "B-018", "cam": "03-13"}, {"floor": "B1F", "lot": "B-017", "cam": "03-13"}, {"floor": "B1F", "lot": "B-016", "cam": "03-13"}] | 2024-10-08 19:01:11 | 2024-10-08
176557 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03014 | 03-14 | 192.42.222.58 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:e2/1728385274_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-14/cam_view_20241008191630.jpg | [{"floor": "B1F", "lot": "A-095", "cam": "03-14"}, {"floor": "B1F", "lot": "A-094", "cam": "03-14"}, {"floor": "B1F", "lot": "A-093", "cam": "03-14"}] | 2024-10-08 19:01:14 | 2024-10-08
176558 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03015 | 03-15 | 192.42.222.59 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:d5/1728385277_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-15/cam_view_20241008191650.jpg | [{"floor": "B1F", "lot": "A-098", "cam": "03-15"}, {"floor": "B1F", "lot": "A-097", "cam": "03-15"}, {"floor": "B1F", "lot": "A-096", "cam": "03-15"}] | 2024-10-08 19:01:16 | 2024-10-08
176559 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch01006 | 01-06 | 192.42.222.6 | 3559 | None | Pass |  |  |  |  | None | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | d0fb81f6d601e3f4447628a367450890 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/2C:A5:9C:09:96:48/20241008_185913.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/01-06/cam_view_20241008190625.jpg | [{"floor": "B1F", "lot": "A-105", "cam": "01-06"}, {"floor": "B1F", "lot": "A-104", "cam": "01-06"}, {"floor": "B1F", "lot": "A-103", "cam": "01-06"}] | 2024-10-08 18:59:12 | 2024-10-08
176560 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03016 | 03-16 | 192.42.222.60 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:dc/1728385279_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-16/cam_view_20241008191711.jpg | [{"floor": "B1F", "lot": "A-102", "cam": "03-16"}, {"floor": "B1F", "lot": "A-101", "cam": "03-16"}, {"floor": "B1F", "lot": "A-100", "cam": "03-16"}] | 2024-10-08 19:01:19 | 2024-10-08
176561 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03017 | 03-17 | 192.42.222.61 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:d8/1728385282_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-17/cam_view_20241008191733.jpg | [{"floor": "B1F", "lot": "A-292", "cam": "03-17"}, {"floor": "B1F", "lot": "A-291", "cam": "03-17"}, {"floor": "B1F", "lot": "A-290", "cam": "03-17"}] | 2024-10-08 19:01:21 | 2024-10-08
176562 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03018 | 03-18 | 192.42.222.62 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:de/1728385284_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-18/cam_view_20241008191752.jpg | [{"floor": "B1F", "lot": "B-221", "cam": "03-18"}, {"floor": "B1F", "lot": "B-220", "cam": "03-18"}, {"floor": "B1F", "lot": "B-219", "cam": "03-18"}] | 2024-10-08 19:01:23 | 2024-10-08
176563 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03019 | 03-19 | 192.42.222.63 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:d9/1728385286_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-19/cam_view_20241008191815.jpg | [{"floor": "B1F", "lot": "B-091", "cam": "03-19"}, {"floor": "B1F", "lot": "B-090", "cam": "03-19"}, {"floor": "B1F", "lot": "B-089", "cam": "03-19"}] | 2024-10-08 19:01:25 | 2024-10-08
176564 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03020 | 03-20 | 192.42.222.64 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:d3/1728385288_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-20/cam_view_20241008191830.jpg | [{"floor": "B1F", "lot": "B-092", "cam": "03-20"}] | 2024-10-08 19:01:28 | 2024-10-08
176565 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03021 | 03-21 | 192.42.222.65 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:e1/1728385291_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-21/cam_view_20241008191904.jpg | [{"floor": "B1F", "lot": "B-088", "cam": "03-21"}, {"floor": "B1F", "lot": "B-087", "cam": "03-21"}, {"floor": "B1F", "lot": "B-086", "cam": "03-21"}] | 2024-10-08 19:01:30 | 2024-10-08
176566 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03022 | 03-22 | 192.42.222.66 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:da/1728385293_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-22/cam_view_20241008191938.jpg | [{"floor": "B1F", "lot": "B-135", "cam": "03-22"}] | 2024-10-08 19:01:33 | 2024-10-08
176567 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03023 | 03-23 | 192.42.222.67 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:d7/1728385295_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-23/cam_view_20241008192009.jpg | [{"floor": "B1F", "lot": "B-218", "cam": "03-23"}, {"floor": "B1F", "lot": "B-217", "cam": "03-23"}, {"floor": "B1F", "lot": "B-216", "cam": "03-23"}] | 2024-10-08 19:01:35 | 2024-10-08
176568 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03024 | 03-24 | 192.42.222.68 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:df/1728385297_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-24/cam_view_20241008192027.jpg | [{"floor": "B1F", "lot": "B-237", "cam": "03-24"}, {"floor": "B1F", "lot": "B-236", "cam": "03-24"}] | 2024-10-08 19:01:37 | 2024-10-08
176569 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03025 | 03-25 | 192.42.222.69 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:e6/1728385300_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-25/cam_view_20241008192044.jpg | [{"floor": "B1F", "lot": "B-235", "cam": "03-25"}, {"floor": "B1F", "lot": "B-234", "cam": "03-25"}, {"floor": "B1F", "lot": "B-233", "cam": "03-25"}] | 2024-10-08 19:01:39 | 2024-10-08
176570 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch01007 | 01-07 | 192.42.222.7 | 3559 | None | Pass |  |  |  |  | None | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | 6b9567acb7f7e344585a3682cfd7ff53 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/2C:A5:9C:09:95:C4/20241008_185916.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/01-07/cam_view_20241008190638.jpg | [] | 2024-10-08 18:59:15 | 2024-10-08
176571 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03026 | 03-26 | 192.42.222.70 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:e5/1728385303_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-26/cam_view_20241008192102.jpg | [{"floor": "B1F", "lot": "B-232", "cam": "03-26"}] | 2024-10-08 19:01:42 | 2024-10-08
176572 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03027 | 03-27 | 192.42.222.71 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:46:88:5a/1728385305_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-27/cam_view_20241008192118.jpg | [{"floor": "B1F", "lot": "B-226", "cam": "03-27"}] | 2024-10-08 19:01:45 | 2024-10-08
176573 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03028 | 03-28 | 192.42.222.72 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:46:88:58/1728385307_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-28/cam_view_20241008192138.jpg | [{"floor": "B1F", "lot": "B-241", "cam": "03-28"}, {"floor": "B1F", "lot": "B-240", "cam": "03-28"}, {"floor": "B1F", "lot": "B-239", "cam": "03-28"}, {"floor": "B1F", "lot": "B-238", "cam": "03-28"}] | 2024-10-08 19:01:46 | 2024-10-08
176574 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03029 | 03-29 | 192.42.222.73 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:46:88:5d/1728385309_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-29/cam_view_20241008192154.jpg | [{"floor": "B1F", "lot": "B-244", "cam": "03-29"}, {"floor": "B1F", "lot": "B-243", "cam": "03-29"}, {"floor": "B1F", "lot": "B-242", "cam": "03-29"}] | 2024-10-08 19:01:48 | 2024-10-08
176575 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03030 | 03-30 | 192.42.222.74 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9b:66/1728385312_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-30/cam_view_20241008192209.jpg | [{"floor": "B1F", "lot": "B-247", "cam": "03-30"}, {"floor": "B1F", "lot": "B-246", "cam": "03-30"}, {"floor": "B1F", "lot": "B-245", "cam": "03-30"}] | 2024-10-08 19:01:51 | 2024-10-08
176576 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03031 | 03-31 | 192.42.222.75 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9b:57/1728385314_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-31/cam_view_20241008192229.jpg | [{"floor": "B1F", "lot": "B-250", "cam": "03-31"}, {"floor": "B1F", "lot": "B-249", "cam": "03-31"}, {"floor": "B1F", "lot": "B-248", "cam": "03-31"}] | 2024-10-08 19:01:54 | 2024-10-08
176577 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03032 | 03-32 | 192.42.222.76 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9b:64/1728385317_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-32/cam_view_20241008192305.jpg | [{"floor": "B1F", "lot": "B-151", "cam": "03-32"}, {"floor": "B1F", "lot": "B-150", "cam": "03-32"}, {"floor": "B1F", "lot": "B-149", "cam": "03-32"}] | 2024-10-08 19:01:57 | 2024-10-08
176578 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03033 | 03-33 | 192.42.222.77 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9b:52/1728385319_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-33/cam_view_20241008192339.jpg | [{"floor": "B1F", "lot": "B-134", "cam": "03-33"}] | 2024-10-08 19:01:59 | 2024-10-08
176579 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03034 | 03-34 | 192.42.222.78 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9b:5f/1728385325_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-34/cam_view_20241008192353.jpg | [{"floor": "B1F", "lot": "B-082", "cam": "03-34"}, {"floor": "B1F", "lot": "B-081", "cam": "03-34"}, {"floor": "B1F", "lot": "B-080", "cam": "03-34"}] | 2024-10-08 19:02:01 | 2024-10-08
176580 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03035 | 03-35 | 192.42.222.79 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9b:47/1728385327_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-35/cam_view_20241008192432.jpg | [{"floor": "B1F", "lot": "B-085", "cam": "03-35"}, {"floor": "B1F", "lot": "B-084", "cam": "03-35"}, {"floor": "B1F", "lot": "B-083", "cam": "03-35"}] | 2024-10-08 19:02:07 | 2024-10-08
176581 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch01008 | 01-08 | 192.42.222.8 | 3559 | None | Pass |  |  |  |  | None | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | e5746c0f6148971601bb31d9486e4c4d | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/2C:A5:9C:09:95:B9/20241008_185918.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/01-08/cam_view_20241008190655.jpg | [] | 2024-10-08 18:59:18 | 2024-10-08
176582 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03036 | 03-36 | 192.42.222.80 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9b:5c/1728385329_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-36/cam_view_20241008192449.jpg | [{"floor": "B1F", "lot": "A-304", "cam": "03-36"}] | 2024-10-08 19:02:09 | 2024-10-08
176583 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03039 | 03-39 | 192.42.222.81 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:f9/1728385337_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-39/cam_view_20241008192549.jpg | [{"floor": "B1F", "lot": "A-179", "cam": "03-39"}, {"floor": "B1F", "lot": "A-178", "cam": "03-39"}, {"floor": "B1F", "lot": "A-177", "cam": "03-39"}] | 2024-10-08 19:02:16 | 2024-10-08
176584 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03065 | 03-65 | 192.42.222.81 | rgl_cam | None | Pass |  |  |  |  | 1 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:f9/1728385415_2.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-65/cam_view_20241008193651.jpg | [{"floor": "B1F", "lot": "A-188", "cam": "03-65"}, {"floor": "B1F", "lot": "A-187", "cam": "03-65"}, {"floor": "B1F", "lot": "A-186", "cam": "03-65"}] | 2024-10-08 19:03:34 | 2024-10-08
176585 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03040 | 03-40 | 192.42.222.82 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:f5/1728385341_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-40/cam_view_20241008192611.jpg | [{"floor": "B1F", "lot": "A-049", "cam": "03-40"}, {"floor": "B1F", "lot": "A-048", "cam": "03-40"}, {"floor": "B1F", "lot": "A-047", "cam": "03-40"}] | 2024-10-08 19:02:20 | 2024-10-08
176586 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03066 | 03-66 | 192.42.222.82 | rgl_cam | None | Pass |  |  |  |  | 1 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:f5/1728385418_2.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-66/cam_view_20241008193720.jpg | [{"floor": "B1F", "lot": "A-039", "cam": "03-66"}, {"floor": "B1F", "lot": "A-038", "cam": "03-66"}, {"floor": "B1F", "lot": "A-037", "cam": "03-66"}] | 2024-10-08 19:03:38 | 2024-10-08
176587 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03041 | 03-41 | 192.42.222.83 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:f1/1728385344_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-41/cam_view_20241008192631.jpg | [{"floor": "B1F", "lot": "A-064", "cam": "03-41"}, {"floor": "B1F", "lot": "A-063", "cam": "03-41"}, {"floor": "B1F", "lot": "A-062", "cam": "03-41"}] | 2024-10-08 19:02:23 | 2024-10-08
176588 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03067 | 03-67 | 192.42.222.83 | rgl_cam | None | Pass |  |  |  |  | 1 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:f1/1728385421_2.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-67/cam_view_20241008193745.jpg | [{"floor": "B1F", "lot": "A-030", "cam": "03-67"}, {"floor": "B1F", "lot": "A-029", "cam": "03-67"}] | 2024-10-08 19:03:41 | 2024-10-08
176589 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03042 | 03-42 | 192.42.222.84 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:f6/1728529861_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-42/cam_view_20241010111115.jpg | [{"floor": "B1F", "lot": "A-009", "cam": "03-42"}, {"floor": "B1F", "lot": "A-008", "cam": "03-42"}, {"floor": "B1F", "lot": "A-007", "cam": "03-42"}] | 2024-10-10 11:11:00 | 2024-10-10
176590 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03068 | 03-68 | 192.42.222.84 | rgl_cam | None | Pass |  |  |  |  | 1 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:f6/1728385424_2.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-68/cam_view_20241008193820.jpg | [{"floor": "B1F", "lot": "A-028", "cam": "03-68"}, {"floor": "B1F", "lot": "A-027", "cam": "03-68"}] | 2024-10-08 19:03:43 | 2024-10-08
176591 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03043 | 03-43 | 192.42.222.85 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:ea/1728529865_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-43/cam_view_20241010111120.jpg | [{"floor": "B1F", "lot": "A-026", "cam": "03-43"}] | 2024-10-10 11:11:05 | 2024-10-10
176592 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03069 | 03-69 | 192.42.222.85 | rgl_cam | None | Pass |  |  |  |  | 1 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:ea/1728385427_2.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-69/cam_view_20241008193844.jpg | [{"floor": "B1F", "lot": "A-006", "cam": "03-69"}, {"floor": "B1F", "lot": "A-005", "cam": "03-69"}, {"floor": "B1F", "lot": "A-004", "cam": "03-69"}] | 2024-10-08 19:03:47 | 2024-10-08
176593 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03044 | 03-44 | 192.42.222.86 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:f4/1728529869_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-44/cam_view_20241010111123.jpg | [{"floor": "B1F", "lot": "A-025", "cam": "03-44"}] | 2024-10-10 11:11:09 | 2024-10-10
176594 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03070 | 03-70 | 192.42.222.86 | rgl_cam | None | Pass |  |  |  |  | 1 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:f4/1728385431_2.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-70/cam_view_20241008193919.jpg | [{"floor": "B1F", "lot": "A-003", "cam": "03-70"}, {"floor": "B1F", "lot": "A-002", "cam": "03-70"}, {"floor": "B1F", "lot": "A-001", "cam": "03-70"}] | 2024-10-08 19:03:50 | 2024-10-08
176595 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03045 | 03-45 | 192.42.222.87 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:ec/1728385353_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-45/cam_view_20241008192846.jpg | [{"floor": "B1F", "lot": "B-032", "cam": "03-45"}] | 2024-10-08 19:02:33 | 2024-10-08
176596 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03071 | 03-71 | 192.42.222.87 | rgl_cam | None | Pass |  |  |  |  | 1 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:ec/1728385435_2.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-71/cam_view_20241008193945.jpg | [{"floor": "B1F", "lot": "B-012", "cam": "03-71"}, {"floor": "B1F", "lot": "B-011", "cam": "03-71"}, {"floor": "B1F", "lot": "B-010", "cam": "03-71"}] | 2024-10-08 19:03:54 | 2024-10-08
176597 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03046 | 03-46 | 192.42.222.88 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:f0/1728385357_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-46/cam_view_20241008192911.jpg | [{"floor": "B1F", "lot": "B-033", "cam": "03-46"}] | 2024-10-08 19:02:36 | 2024-10-08
176598 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03072 | 03-72 | 192.42.222.88 | rgl_cam | None | Pass |  |  |  |  | 1 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:f0/1728385438_2.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-72/cam_view_20241008194017.jpg | [{"floor": "B1F", "lot": "B-015", "cam": "03-72"}, {"floor": "B1F", "lot": "B-014", "cam": "03-72"}, {"floor": "B1F", "lot": "B-013", "cam": "03-72"}] | 2024-10-08 19:03:57 | 2024-10-08
176599 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03047 | 03-47 | 192.42.222.89 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:f8/1728385359_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-47/cam_view_20241008192929.jpg | [{"floor": "B1F", "lot": "A-170", "cam": "03-47"}, {"floor": "B1F", "lot": "A-169", "cam": "03-47"}, {"floor": "B1F", "lot": "A-168", "cam": "03-47"}] | 2024-10-08 19:02:39 | 2024-10-08
176600 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03073 | 03-73 | 192.42.222.89 | rgl_cam | None | Pass |  |  |  |  | 1 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:f8/1728385441_2.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-73/cam_view_20241008194044.jpg | [{"floor": "B1F", "lot": "A-161", "cam": "03-73"}, {"floor": "B1F", "lot": "A-160", "cam": "03-73"}] | 2024-10-08 19:04:01 | 2024-10-08
176601 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch01009 | 01-09 | 192.42.222.9 | 3559 | None | Pass |  |  |  |  | None | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | 19a3623df064b6ce003bc79a7879ba32 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/2C:A5:9C:09:95:A7/20241008_185920.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/01-09/cam_view_20241008190714.jpg | [] | 2024-10-08 18:59:20 | 2024-10-08
176602 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03048 | 03-48 | 192.42.222.90 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:f2/1728385363_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-48/cam_view_20241008192953.jpg | [{"floor": "B1F", "lot": "A-173", "cam": "03-48"}, {"floor": "B1F", "lot": "A-172", "cam": "03-48"}, {"floor": "B1F", "lot": "A-171", "cam": "03-48"}] | 2024-10-08 19:02:42 | 2024-10-08
176603 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03074 | 03-74 | 192.42.222.90 | rgl_cam | None | Pass |  |  |  |  | 1 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:f2/1728385444_2.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-74/cam_view_20241008194129.jpg | [{"floor": "B1F", "lot": "A-159", "cam": "03-74"}, {"floor": "B1F", "lot": "A-158", "cam": "03-74"}, {"floor": "B1F", "lot": "A-157", "cam": "03-74"}] | 2024-10-08 19:04:04 | 2024-10-08
176604 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03049 | 03-49 | 192.42.222.91 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:ed/1728385366_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-49/cam_view_20241008193029.jpg | [{"floor": "B1F", "lot": "A-176", "cam": "03-49"}, {"floor": "B1F", "lot": "A-175", "cam": "03-49"}, {"floor": "B1F", "lot": "A-174", "cam": "03-49"}] | 2024-10-08 19:02:45 | 2024-10-08
176605 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03075 | 03-75 | 192.42.222.91 | rgl_cam | None | Pass |  |  |  |  | 1 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:ed/1728385447_2.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-75/cam_view_20241008194215.jpg | [] | 2024-10-08 19:04:07 | 2024-10-08
176606 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03050 | 03-50 | 192.42.222.92 | rgl_cam | None | Fail |  |  | [相机]画面被遮挡--交付经理 |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:f7/1728385369_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-50/cam_view_20241008193053.jpg | [{"floor": "B1F", "lot": "A-194", "cam": "03-50"}, {"floor": "B1F", "lot": "A-193", "cam": "03-50"}, {"floor": "B1F", "lot": "A-192", "cam": "03-50"}] | 2024-10-08 19:02:49 | 2024-10-08
176607 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03076 | 03-76 | 192.42.222.92 | rgl_cam | None | Pass |  |  |  |  | 1 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:f7/1728385450_2.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-76/cam_view_20241008194238.jpg | [{"floor": "B1F", "lot": "A-205", "cam": "03-76"}, {"floor": "B1F", "lot": "A-204", "cam": "03-76"}, {"floor": "B1F", "lot": "A-203", "cam": "03-76"}] | 2024-10-08 19:04:10 | 2024-10-08
176608 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03051 | 03-51 | 192.42.222.93 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:ee/1728385373_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-51/cam_view_20241008193116.jpg | [{"floor": "B1F", "lot": "B-153", "cam": "03-51"}, {"floor": "B1F", "lot": "B-152", "cam": "03-51"}] | 2024-10-08 19:02:52 | 2024-10-08
176609 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03077 | 03-77 | 192.42.222.93 | rgl_cam | None | Pass |  |  |  |  | 1 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:ee/1728385454_2.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-77/cam_view_20241008194258.jpg | [{"floor": "B1F", "lot": "B-148", "cam": "03-77"}, {"floor": "B1F", "lot": "B-147", "cam": "03-77"}, {"floor": "B1F", "lot": "B-146", "cam": "03-77"}] | 2024-10-08 19:04:13 | 2024-10-08
176610 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03052 | 03-52 | 192.42.222.94 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:eb/1728385376_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-52/cam_view_20241008193136.jpg | [{"floor": "B1F", "lot": "B-156", "cam": "03-52"}, {"floor": "B1F", "lot": "B-155", "cam": "03-52"}, {"floor": "B1F", "lot": "B-154", "cam": "03-52"}] | 2024-10-08 19:02:55 | 2024-10-08
176611 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03078 | 03-78 | 192.42.222.94 | rgl_cam | None | Pass |  |  |  |  | 1 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:eb/1728385457_2.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-78/cam_view_20241008194323.jpg | [{"floor": "B1F", "lot": "B-145", "cam": "03-78"}, {"floor": "B1F", "lot": "B-144", "cam": "03-78"}, {"floor": "B1F", "lot": "B-143", "cam": "03-78"}] | 2024-10-08 19:04:16 | 2024-10-08
176612 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03053 | 03-53 | 192.42.222.95 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:e9/1728385379_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-53/cam_view_20241008193209.jpg | [{"floor": "B1F", "lot": "B-142", "cam": "03-53"}, {"floor": "B1F", "lot": "B-141", "cam": "03-53"}, {"floor": "B1F", "lot": "B-140", "cam": "03-53"}] | 2024-10-08 19:02:59 | 2024-10-08
176613 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03079 | 03-79 | 192.42.222.95 | rgl_cam | None | Pass |  |  |  |  | 1 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:e9/1728385461_2.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-79/cam_view_20241008194351.jpg | [{"floor": "B1F", "lot": "B-130", "cam": "03-79"}, {"floor": "B1F", "lot": "B-129", "cam": "03-79"}, {"floor": "B1F", "lot": "B-128", "cam": "03-79"}] | 2024-10-08 19:04:20 | 2024-10-08
176614 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03054 | 03-54 | 192.42.222.96 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:fa/1728385383_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-54/cam_view_20241008193237.jpg | [{"floor": "B1F", "lot": "B-133", "cam": "03-54"}, {"floor": "B1F", "lot": "B-132", "cam": "03-54"}, {"floor": "B1F", "lot": "B-131", "cam": "03-54"}] | 2024-10-08 19:03:03 | 2024-10-08
176615 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03080 | 03-80 | 192.42.222.96 | rgl_cam | None | Pass |  |  |  |  | 1 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:47:9a:fa/1728385464_2.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-80/cam_view_20241008194422.jpg | [{"floor": "B1F", "lot": "B-139", "cam": "03-80"}, {"floor": "B1F", "lot": "B-138", "cam": "03-80"}, {"floor": "B1F", "lot": "B-137", "cam": "03-80"}] | 2024-10-08 19:04:23 | 2024-10-08
176616 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03055 | 03-55 | 192.42.222.97 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:43:b4:01/1728385386_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-55/cam_view_20241008193259.jpg | [{"floor": "B1F", "lot": "A-202", "cam": "03-55"}, {"floor": "B1F", "lot": "A-201", "cam": "03-55"}, {"floor": "B1F", "lot": "A-200", "cam": "03-55"}] | 2024-10-08 19:03:06 | 2024-10-08
176617 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03081 | 03-81 | 192.42.222.97 | rgl_cam | None | Fail |  |  | [相机]画面被遮挡--交付经理 |  | 1 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:43:b4:01/1728385467_2.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-81/cam_view_20241008194451.jpg | [{"floor": "B1F", "lot": "A-197", "cam": "03-81"}, {"floor": "B1F", "lot": "A-196", "cam": "03-81"}, {"floor": "B1F", "lot": "A-195", "cam": "03-81"}] | 2024-10-08 19:04:27 | 2024-10-08
176618 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03056 | 03-56 | 192.42.222.98 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:43:b3:fa/1728385390_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-56/cam_view_20241008193324.jpg | [{"floor": "B1F", "lot": "B-127", "cam": "03-56"}, {"floor": "B1F", "lot": "B-126", "cam": "03-56"}, {"floor": "B1F", "lot": "B-125", "cam": "03-56"}] | 2024-10-08 19:03:09 | 2024-10-08
176619 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03082 | 03-82 | 192.42.222.98 | rgl_cam | None | Pass |  |  |  |  | 1 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:43:b3:fa/1728385470_2.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-82/cam_view_20241008194512.jpg | [{"floor": "B1F", "lot": "B-112", "cam": "03-82"}, {"floor": "B1F", "lot": "B-111", "cam": "03-82"}, {"floor": "B1F", "lot": "B-110", "cam": "03-82"}] | 2024-10-08 19:04:30 | 2024-10-08
176620 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03057 | 03-57 | 192.42.222.99 | rgl_cam | None | Pass |  |  |  |  | 0 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:43:b3:f7/1728385394_1.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-57/cam_view_20241008193347.jpg | [{"floor": "B1F", "lot": "B-115", "cam": "03-57"}, {"floor": "B1F", "lot": "B-114", "cam": "03-57"}, {"floor": "B1F", "lot": "B-113", "cam": "03-57"}] | 2024-10-08 19:03:13 | 2024-10-08
176621 | WUIKApark_klmy_binhe | 克拉玛依汇嘉滨河广场停车场 | WUIKApark_klmy_binhe | B1F | ch03083 | 03-83 | 192.42.222.99 | rgl_cam | None | Pass |  |  |  |  | 1 | 28305a7d-0caa-41bb-8bc2-3e75157cda74 | None | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/bc:5e:33:43:b3:f7/1728385473_2.jpg | https://bj.bcebos.com/camera-manage/debug/WUIKApark_klmy_binhe/projection/03-83/cam_view_20241008194532.jpg | [{"floor": "B1F", "lot": "B-124", "cam": "03-83"}, {"floor": "B1F", "lot": "B-123", "cam": "03-83"}, {"floor": "B1F", "lot": "B-122", "cam": "03-83"}] | 2024-10-08 19:04:33 | 2024-10-08