## 测试报告
停车场 | 测试日期 | 测试类型
中关村壹号IC-PARK园区 | 2025-01-08 | 摄像头检查
总数 | 3559相机 | 红绿灯相机
27 | 27 | 0
Pass | Fail | Untest
23 | 3 | 1
错误类型 | 数目
[相机]相机轻微移动，车位投影线和实际车位线误差10%~30%-天津标定 | 2
[相机]相机严重被撞-交付经理 | 1

## 测试结果
id | parking | parking_name | site_id | floor | cam_channel | cam_short | cam_ip | cam_type | lots | result | comment | resolve | case_assign | case_status | rgl_index | task_id | device | camera_img | debug_img | cam_lots | test_time | test_date | track_img
206464 | zgcyh_beijing_icyq | 中关村壹号IC-PARK园区 | zgcyh_beijing_icyq | B1F | ch01001 | 01-01 | 192.168.254.1 | 3559 | None | Pass |  |  |  |  | None | 15e66a97-e7d9-4c29-b5a8-5dd52f87e9d8 | fc53d6207ef4020a7d7f648ba009ed75 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/24%3A0F%3A9B%3A54%3AF3%3AE5/20250106_173108.jpg?AWSAccessKeyId=LTAI5t8MATbKVpTSR8isTpHc&Signature=0O4b%2BIGz8G%2F6A8aVv35db0uMz9w%3D&Expires=3312955869 | https://bj.bcebos.com/camera-manage/debug/zgcyh_beijing_icyq/projection/01-01/cam_view_20250106173229.jpg | [{"floor": "B1F", "lot": "1184", "cam": "01-01"}, {"floor": "B1F", "lot": "1183", "cam": "01-01"}, {"floor": "B1F", "lot": "1182", "cam": "01-01"}, {"floor": "B1F", "lot": "1181", "cam": "01-01"}, {"floor": "B1F", "lot": "1180", "cam": "01-01"}, {"floor": "B1F", "lot": "1179", "cam": "01-01"}, {"floor": "B1F", "lot": "1127", "cam": "01-01"}, {"floor": "B1F", "lot": "1126", "cam": "01-01"}, {"floor": "B1F", "lot": "1125", "cam": "01-01"}] | 2025-01-06 17:31:08 | 2025-01-06 | None
206465 | zgcyh_beijing_icyq | 中关村壹号IC-PARK园区 | zgcyh_beijing_icyq | B1F | ch01010 | 01-10 | 192.168.254.10 | 3559 | None | Pass |  |  |  |  | None | 15e66a97-e7d9-4c29-b5a8-5dd52f87e9d8 | 7b34442f86cbc69609ca7e3b76feca1f | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/24%3A0F%3A9B%3A54%3AF4%3A2A/20250106_173133.jpg?AWSAccessKeyId=LTAI5t8MATbKVpTSR8isTpHc&Signature=wMU6FfvxzgNLhwt0%2FBeJLqS71js%3D&Expires=3312955894 | https://bj.bcebos.com/camera-manage/debug/zgcyh_beijing_icyq/projection/01-10/cam_view_20250106173530.jpg | [] | 2025-01-06 17:31:32 | 2025-01-06 | None
206466 | zgcyh_beijing_icyq | 中关村壹号IC-PARK园区 | zgcyh_beijing_icyq | B1F | ch01011 | 01-11 | 192.168.254.11 | 3559 | None | Pass |  |  |  |  | None | 15e66a97-e7d9-4c29-b5a8-5dd52f87e9d8 | 285d77afda05e451a185551326f0d111 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/24%3A0F%3A9B%3A54%3AF3%3AE7/20250106_173135.jpg?AWSAccessKeyId=LTAI5t8MATbKVpTSR8isTpHc&Signature=pvQpU6TU9lmdgHyR8ATGn2NEO9M%3D&Expires=3312955896 | https://bj.bcebos.com/camera-manage/debug/zgcyh_beijing_icyq/projection/01-11/cam_view_20250106173545.jpg | [] | 2025-01-06 17:31:34 | 2025-01-06 | None
206467 | zgcyh_beijing_icyq | 中关村壹号IC-PARK园区 | zgcyh_beijing_icyq | B1F | ch01012 | 01-12 | 192.168.254.12 | 3559 | None | Pass |  |  |  |  | None | 15e66a97-e7d9-4c29-b5a8-5dd52f87e9d8 | bd375cfa5ee4b93521b7481f996a1fdd | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/24%3A0F%3A9B%3A54%3AF3%3ADB/20250106_173138.jpg?AWSAccessKeyId=LTAI5t8MATbKVpTSR8isTpHc&Signature=7LE8%2FHaqGKXRP3XPwzTmTgeYvgw%3D&Expires=3312955898 | https://bj.bcebos.com/camera-manage/debug/zgcyh_beijing_icyq/projection/01-12/cam_view_20250106173602.jpg | [] | 2025-01-06 17:31:37 | 2025-01-06 | None
206468 | zgcyh_beijing_icyq | 中关村壹号IC-PARK园区 | zgcyh_beijing_icyq | B1F | ch01013 | 01-13 | 192.168.254.13 | 3559 | None | Pass |  |  |  |  | None | 15e66a97-e7d9-4c29-b5a8-5dd52f87e9d8 | 763d128a80c7ad1fefcfb7830f65b770 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/24%3A0F%3A9B%3A54%3AF4%3A11/20250106_173140.jpg?AWSAccessKeyId=LTAI5t8MATbKVpTSR8isTpHc&Signature=Aobuecd7vXvB%2BYJQmNiGiEW3gz4%3D&Expires=3312955901 | https://bj.bcebos.com/camera-manage/debug/zgcyh_beijing_icyq/projection/01-13/cam_view_20250106173617.jpg | [] | 2025-01-06 17:31:39 | 2025-01-06 | None
206469 | zgcyh_beijing_icyq | 中关村壹号IC-PARK园区 | zgcyh_beijing_icyq | B1F | ch01014 | 01-14 | 192.168.254.14 | 3559 | None | Pass |  |  |  |  | None | 15e66a97-e7d9-4c29-b5a8-5dd52f87e9d8 | 35e2484921a10842d5b482d786e10876 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/24%3A0F%3A9B%3A4B%3A7C%3A98/20250106_173144.jpg?AWSAccessKeyId=LTAI5t8MATbKVpTSR8isTpHc&Signature=Jp7XowUNX8ayIFQ%2BDFU7OV%2Bv%2Bxg%3D&Expires=3312955904 | https://bj.bcebos.com/camera-manage/debug/zgcyh_beijing_icyq/projection/01-14/cam_view_20250106173631.jpg | [] | 2025-01-06 17:31:43 | 2025-01-06 | None
206470 | zgcyh_beijing_icyq | 中关村壹号IC-PARK园区 | zgcyh_beijing_icyq | B1F | ch01015 | 01-15 | 192.168.254.15 | 3559 | None | Pass |  |  |  |  | None | 15e66a97-e7d9-4c29-b5a8-5dd52f87e9d8 | b8033272c0da0a992195929d807d5607 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/24%3A0F%3A9B%3A4B%3A7B%3AAA/20250106_173146.jpg?AWSAccessKeyId=LTAI5t8MATbKVpTSR8isTpHc&Signature=Yfmhmr8p6%2F9303WQUjmUP4VCldI%3D&Expires=3312955906 | https://bj.bcebos.com/camera-manage/debug/zgcyh_beijing_icyq/projection/01-15/cam_view_20250106173655.jpg | [{"floor": "B1F", "lot": "1046", "cam": "01-15"}, {"floor": "B1F", "lot": "1045", "cam": "01-15"}, {"floor": "B1F", "lot": "1044", "cam": "01-15"}, {"floor": "B1F", "lot": "1043", "cam": "01-15"}, {"floor": "B1F", "lot": "1042", "cam": "01-15"}, {"floor": "B1F", "lot": "1041", "cam": "01-15"}] | 2025-01-06 17:31:45 | 2025-01-06 | None
206471 | zgcyh_beijing_icyq | 中关村壹号IC-PARK园区 | zgcyh_beijing_icyq | B1F | ch01016 | 01-16 | 192.168.254.16 | 3559 | None | Pass |  |  |  |  | None | 15e66a97-e7d9-4c29-b5a8-5dd52f87e9d8 | 80bdd0499b3f84e959b90d64937c2678 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/24%3A0F%3A9B%3A54%3AF1%3A6F/20250106_173148.jpg?AWSAccessKeyId=LTAI5t8MATbKVpTSR8isTpHc&Signature=zbWrwUNmMuNXY43NeCSpunsyPdY%3D&Expires=3312955908 | https://bj.bcebos.com/camera-manage/debug/zgcyh_beijing_icyq/projection/01-16/cam_view_20250106173709.jpg | [{"floor": "B1F", "lot": "1030", "cam": "01-16"}, {"floor": "B1F", "lot": "1028", "cam": "01-16"}, {"floor": "B1F", "lot": "1027", "cam": "01-16"}, {"floor": "B1F", "lot": "1026", "cam": "01-16"}, {"floor": "B1F", "lot": "1025", "cam": "01-16"}] | 2025-01-06 17:31:47 | 2025-01-06 | None
206472 | zgcyh_beijing_icyq | 中关村壹号IC-PARK园区 | zgcyh_beijing_icyq | B1F | ch01017 | 01-17 | 192.168.254.17 | 3559 | None | Pass |  |  |  |  | None | 15e66a97-e7d9-4c29-b5a8-5dd52f87e9d8 | 4caf7753f74f7a47bd0ea74f89e4944f | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/24%3A0F%3A9B%3A54%3AF0%3AE4/20250106_173149.jpg?AWSAccessKeyId=LTAI5t8MATbKVpTSR8isTpHc&Signature=fr77VfYTxqjVxSjgDmUMlikecuY%3D&Expires=3312955910 | https://bj.bcebos.com/camera-manage/debug/zgcyh_beijing_icyq/projection/01-17/cam_view_20250106173729.jpg | [{"floor": "B1F", "lot": "1107", "cam": "01-17"}, {"floor": "B1F", "lot": "1106", "cam": "01-17"}, {"floor": "B1F", "lot": "1105", "cam": "01-17"}] | 2025-01-06 17:31:49 | 2025-01-06 | None
206473 | zgcyh_beijing_icyq | 中关村壹号IC-PARK园区 | zgcyh_beijing_icyq | B1F | ch01018 | 01-18 | 192.168.254.18 | 3559 | None | Fail |  |  | [相机]相机严重被撞-交付经理 |  | None | 15e66a97-e7d9-4c29-b5a8-5dd52f87e9d8 | 580127ccd47e8523eddadd325dc88f54 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/24%3A0F%3A9B%3A4B%3A7B%3AAF/20250106_173151.jpg?AWSAccessKeyId=LTAI5t8MATbKVpTSR8isTpHc&Signature=sd%2BJNprCztEn4Sh38hblPocNi58%3D&Expires=3312955912 | https://bj.bcebos.com/camera-manage/debug/zgcyh_beijing_icyq/projection/01-18/cam_view_20250106173743.jpg | [{"floor": "B1F", "lot": "1008", "cam": "01-18"}, {"floor": "B1F", "lot": "1007", "cam": "01-18"}, {"floor": "B1F", "lot": "1006", "cam": "01-18"}, {"floor": "B1F", "lot": "1005", "cam": "01-18"}, {"floor": "B1F", "lot": "1004", "cam": "01-18"}, {"floor": "B1F", "lot": "1003", "cam": "01-18"}, {"floor": "B1F", "lot": "1002", "cam": "01-18"}, {"floor": "B1F", "lot": "1001", "cam": "01-18"}] | 2025-01-06 17:31:50 | 2025-01-06 | None
206474 | zgcyh_beijing_icyq | 中关村壹号IC-PARK园区 | zgcyh_beijing_icyq | B1F | ch01019 | 01-19 | 192.168.254.19 | 3559 | None | Fail |  |  | [相机]相机轻微移动，车位投影线和实际车位线误差10%~30%-天津标定 |  | None | 15e66a97-e7d9-4c29-b5a8-5dd52f87e9d8 | dde03a8cacbdcf1850263359d996993e | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/24%3A0F%3A9B%3A54%3AF1%3AFE/20250106_173154.jpg?AWSAccessKeyId=LTAI5t8MATbKVpTSR8isTpHc&Signature=aD8QSBw%2B0dZjZfptf1KOXjquOH4%3D&Expires=3312955914 | https://bj.bcebos.com/camera-manage/debug/zgcyh_beijing_icyq/projection/01-19/cam_view_20250106173757.jpg | [{"floor": "B1F", "lot": "1024", "cam": "01-19"}, {"floor": "B1F", "lot": "1023", "cam": "01-19"}, {"floor": "B1F", "lot": "1022", "cam": "01-19"}, {"floor": "B1F", "lot": "1021", "cam": "01-19"}, {"floor": "B1F", "lot": "1020", "cam": "01-19"}, {"floor": "B1F", "lot": "1019", "cam": "01-19"}, {"floor": "B1F", "lot": "1018", "cam": "01-19"}] | 2025-01-06 17:31:53 | 2025-01-06 | None
206475 | zgcyh_beijing_icyq | 中关村壹号IC-PARK园区 | zgcyh_beijing_icyq | B1F | ch01002 | 01-02 | 192.168.254.2 | 3559 | None | Pass |  |  |  |  | None | 15e66a97-e7d9-4c29-b5a8-5dd52f87e9d8 | 0ea1385420b19f1373256b4b83498eec | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/24%3A0F%3A9B%3A54%3AF3%3AF0/20250106_173111.jpg?AWSAccessKeyId=LTAI5t8MATbKVpTSR8isTpHc&Signature=XEv1I5aHSaGo0r70kcZ29gFMgd4%3D&Expires=3312955871 | https://bj.bcebos.com/camera-manage/debug/zgcyh_beijing_icyq/projection/01-02/cam_view_20250106173244.jpg | [{"floor": "B1F", "lot": "1118", "cam": "01-02"}, {"floor": "B1F", "lot": "1117", "cam": "01-02"}, {"floor": "B1F", "lot": "1116", "cam": "01-02"}] | 2025-01-06 17:31:10 | 2025-01-06 | None
206476 | zgcyh_beijing_icyq | 中关村壹号IC-PARK园区 | zgcyh_beijing_icyq | B1F | ch01020 | 01-20 | 192.168.254.20 | 3559 | None | Pass |  |  |  |  | None | 15e66a97-e7d9-4c29-b5a8-5dd52f87e9d8 | b2b28ec85409b98a6f540150352c6f02 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/24%3A0F%3A9B%3A4B%3A7B%3A42/20250106_173156.jpg?AWSAccessKeyId=LTAI5t8MATbKVpTSR8isTpHc&Signature=Zbh8eprlj6tRZuV2yKqJkpVW2GM%3D&Expires=3312955917 | https://bj.bcebos.com/camera-manage/debug/zgcyh_beijing_icyq/projection/01-20/cam_view_20250106173814.jpg | [{"floor": "B1F", "lot": "1088", "cam": "01-20"}, {"floor": "B1F", "lot": "1087", "cam": "01-20"}, {"floor": "B1F", "lot": "1086", "cam": "01-20"}, {"floor": "B1F", "lot": "1033", "cam": "01-20"}, {"floor": "B1F", "lot": "1032", "cam": "01-20"}, {"floor": "B1F", "lot": "1031", "cam": "01-20"}] | 2025-01-06 17:31:56 | 2025-01-06 | None
206477 | zgcyh_beijing_icyq | 中关村壹号IC-PARK园区 | zgcyh_beijing_icyq | B1F | ch01021 | 01-21 | 192.168.254.21 | 3559 | None | Pass |  |  |  |  | None | 15e66a97-e7d9-4c29-b5a8-5dd52f87e9d8 | 40565f3425b2d733a23aa7ec8bee910f | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/24%3A0F%3A9B%3A54%3AF3%3AFB/20250106_173158.jpg?AWSAccessKeyId=LTAI5t8MATbKVpTSR8isTpHc&Signature=LXq5lZzWg66NS%2FwTSNBOKTbqvIM%3D&Expires=3312955918 | https://bj.bcebos.com/camera-manage/debug/zgcyh_beijing_icyq/projection/01-21/cam_view_20250106173835.jpg | [{"floor": "B1F", "lot": "1091", "cam": "01-21"}, {"floor": "B1F", "lot": "1089", "cam": "01-21"}, {"floor": "B1F", "lot": "1029", "cam": "01-21"}] | 2025-01-06 17:31:57 | 2025-01-06 | None
206478 | zgcyh_beijing_icyq | 中关村壹号IC-PARK园区 | zgcyh_beijing_icyq | B1F | ch01022 | 01-22 | 192.168.254.22 | 3559 | None | Pass |  |  |  |  | None | 15e66a97-e7d9-4c29-b5a8-5dd52f87e9d8 | 80d560d37b1425c13ace666f079d4bc9 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/24%3A0F%3A9B%3A54%3AF0%3A76/20250106_173200.jpg?AWSAccessKeyId=LTAI5t8MATbKVpTSR8isTpHc&Signature=SVAtWaFi994Pl0k0aruCT73zSXI%3D&Expires=3312955921 | https://bj.bcebos.com/camera-manage/debug/zgcyh_beijing_icyq/projection/01-22/cam_view_20250106173854.jpg | [{"floor": "B1F", "lot": "1082", "cam": "01-22"}, {"floor": "B1F", "lot": "1081", "cam": "01-22"}, {"floor": "B1F", "lot": "1080", "cam": "01-22"}, {"floor": "B1F", "lot": "1079", "cam": "01-22"}, {"floor": "B1F", "lot": "1078", "cam": "01-22"}, {"floor": "B1F", "lot": "1040", "cam": "01-22"}, {"floor": "B1F", "lot": "1039", "cam": "01-22"}, {"floor": "B1F", "lot": "1038", "cam": "01-22"}] | 2025-01-06 17:31:59 | 2025-01-06 | None
206479 | zgcyh_beijing_icyq | 中关村壹号IC-PARK园区 | zgcyh_beijing_icyq | B1F | ch01023 | 01-23 | 192.168.254.23 | 3559 | None | Pass |  |  |  |  | None | 15e66a97-e7d9-4c29-b5a8-5dd52f87e9d8 | d222b80757fb9eb70f1b85c8059611f5 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/24%3A0F%3A9B%3A54%3AEF%3ABF/20250106_173203.jpg?AWSAccessKeyId=LTAI5t8MATbKVpTSR8isTpHc&Signature=uVFChbVdlWlRVxrarXL54X1f8eA%3D&Expires=3312955924 | https://bj.bcebos.com/camera-manage/debug/zgcyh_beijing_icyq/projection/01-23/cam_view_20250106173944.jpg | [] | 2025-01-06 17:32:02 | 2025-01-06 | None
206480 | zgcyh_beijing_icyq | 中关村壹号IC-PARK园区 | zgcyh_beijing_icyq | B1F | ch01024 | 01-24 | 192.168.254.24 | 3559 | None | Pass |  |  |  |  | None | 15e66a97-e7d9-4c29-b5a8-5dd52f87e9d8 | c872f68a98b05c2577d1e12fa14d9e97 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/24%3A0F%3A9B%3A4B%3A7B%3A82/20250106_173205.jpg?AWSAccessKeyId=LTAI5t8MATbKVpTSR8isTpHc&Signature=Ny4yp8gJZgHjQH9cpaclcSDkx30%3D&Expires=3312955926 | https://bj.bcebos.com/camera-manage/debug/zgcyh_beijing_icyq/projection/01-24/cam_view_20250106174002.jpg | [{"floor": "B1F", "lot": "1037", "cam": "01-24"}, {"floor": "B1F", "lot": "1036", "cam": "01-24"}] | 2025-01-06 17:32:05 | 2025-01-06 | None
206481 | zgcyh_beijing_icyq | 中关村壹号IC-PARK园区 | zgcyh_beijing_icyq | B1F | ch01025 | 01-25 | 192.168.254.25 | 3559 | None | Pass |  |  |  |  | None | 15e66a97-e7d9-4c29-b5a8-5dd52f87e9d8 | 3124989178f43c6258c039880a5a77a1 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/24%3A0F%3A9B%3A4B%3A7C%3A76/20250106_173207.jpg?AWSAccessKeyId=LTAI5t8MATbKVpTSR8isTpHc&Signature=KVtd6znNLTMu7mBiNLE%2BgKuFcAA%3D&Expires=3312955927 | https://bj.bcebos.com/camera-manage/debug/zgcyh_beijing_icyq/projection/01-25/cam_view_20250106174021.jpg | [{"floor": "B1F", "lot": "1062", "cam": "01-25"}, {"floor": "B1F", "lot": "1061", "cam": "01-25"}, {"floor": "B1F", "lot": "1060", "cam": "01-25"}, {"floor": "B1F", "lot": "1059", "cam": "01-25"}, {"floor": "B1F", "lot": "1058", "cam": "01-25"}, {"floor": "B1F", "lot": "1057", "cam": "01-25"}, {"floor": "B1F", "lot": "1056", "cam": "01-25"}, {"floor": "B1F", "lot": "1055", "cam": "01-25"}] | 2025-01-06 17:32:06 | 2025-01-06 | None
206482 | zgcyh_beijing_icyq | 中关村壹号IC-PARK园区 | zgcyh_beijing_icyq | B1F | ch01026 | 01-26 | 192.168.254.26 | 3559 | None | Fail |  |  | [相机]相机轻微移动，车位投影线和实际车位线误差10%~30%-天津标定 |  | None | 15e66a97-e7d9-4c29-b5a8-5dd52f87e9d8 | d20f2abb53e32a86e30961079209bf79 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/24%3A0F%3A9B%3A4B%3A7C%3A3D/20250106_173208.jpg?AWSAccessKeyId=LTAI5t8MATbKVpTSR8isTpHc&Signature=K5lnw9Hd%2FqIW7TfPYjLUa%2FEKF9Q%3D&Expires=3312955929 | https://bj.bcebos.com/camera-manage/debug/zgcyh_beijing_icyq/projection/01-26/cam_view_20250106174043.jpg | [{"floor": "B1F", "lot": "1068", "cam": "01-26"}, {"floor": "B1F", "lot": "1067", "cam": "01-26"}, {"floor": "B1F", "lot": "1066", "cam": "01-26"}, {"floor": "B1F", "lot": "1064", "cam": "01-26"}, {"floor": "B1F", "lot": "1063", "cam": "01-26"}, {"floor": "B1F", "lot": "1054", "cam": "01-26"}, {"floor": "B1F", "lot": "1053", "cam": "01-26"}] | 2025-01-06 17:32:08 | 2025-01-06 | None
206483 | zgcyh_beijing_icyq | 中关村壹号IC-PARK园区 | zgcyh_beijing_icyq | B1F | ch01027 | 01-27 | 192.168.254.27 | 3559 | None | Pass |  |  |  |  | None | 15e66a97-e7d9-4c29-b5a8-5dd52f87e9d8 | 0fea8286c425ca2d4e994abaecb8827e | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/24%3A0F%3A9B%3A4B%3A7C%3AA1/20250106_173210.jpg?AWSAccessKeyId=LTAI5t8MATbKVpTSR8isTpHc&Signature=RjF0zfM%2BiDZGEZKwboGIkeQ0cAs%3D&Expires=3312955931 | https://bj.bcebos.com/camera-manage/debug/zgcyh_beijing_icyq/projection/01-27/cam_view_20250106174058.jpg | [{"floor": "B1F", "lot": "1034", "cam": "01-27"}, {"floor": "B1F", "lot": "1016", "cam": "01-27"}, {"floor": "B1F", "lot": "1015", "cam": "01-27"}, {"floor": "B1F", "lot": "1014", "cam": "01-27"}, {"floor": "B1F", "lot": "1013", "cam": "01-27"}, {"floor": "B1F", "lot": "1012", "cam": "01-27"}] | 2025-01-06 17:32:10 | 2025-01-06 | None
206484 | zgcyh_beijing_icyq | 中关村壹号IC-PARK园区 | zgcyh_beijing_icyq | B1F | ch01003 | 01-03 | 192.168.254.3 | 3559 | None | Pass |  |  |  |  | None | 15e66a97-e7d9-4c29-b5a8-5dd52f87e9d8 | 85d6d3734a387801a567f9460b162d78 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/24%3A0F%3A9B%3A54%3AF0%3A51/20250106_173115.jpg?AWSAccessKeyId=LTAI5t8MATbKVpTSR8isTpHc&Signature=gQ5DrWHvvgfxVxmrbNp16lGOJ%2FE%3D&Expires=3312955875 | https://bj.bcebos.com/camera-manage/debug/zgcyh_beijing_icyq/projection/01-03/cam_view_20250106173259.jpg | [{"floor": "B1F", "lot": "1168", "cam": "01-03"}, {"floor": "B1F", "lot": "1167", "cam": "01-03"}, {"floor": "B1F", "lot": "1166", "cam": "01-03"}, {"floor": "B1F", "lot": "1165", "cam": "01-03"}, {"floor": "B1F", "lot": "1135", "cam": "01-03"}, {"floor": "B1F", "lot": "1134", "cam": "01-03"}] | 2025-01-06 17:31:14 | 2025-01-06 | None
206485 | zgcyh_beijing_icyq | 中关村壹号IC-PARK园区 | zgcyh_beijing_icyq | B1F | ch01004 | 01-04 | 192.168.254.4 | 3559 | None | Pass |  |  |  |  | None | 15e66a97-e7d9-4c29-b5a8-5dd52f87e9d8 | 379edd5606aa60c4df965f2f58c7dea5 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/24%3A0F%3A9B%3A54%3AF0%3A73/20250106_173117.jpg?AWSAccessKeyId=LTAI5t8MATbKVpTSR8isTpHc&Signature=5H3i7b3tGf84nV91GE9E9DgTar4%3D&Expires=3312955878 | https://bj.bcebos.com/camera-manage/debug/zgcyh_beijing_icyq/projection/01-04/cam_view_20250106173313.jpg | [{"floor": "B1F", "lot": "1115", "cam": "01-04"}, {"floor": "B1F", "lot": "1114", "cam": "01-04"}, {"floor": "B1F", "lot": "1113", "cam": "01-04"}, {"floor": "B1F", "lot": "1112", "cam": "01-04"}, {"floor": "B1F", "lot": "1111", "cam": "01-04"}, {"floor": "B1F", "lot": "1110", "cam": "01-04"}, {"floor": "B1F", "lot": "1109", "cam": "01-04"}] | 2025-01-06 17:31:16 | 2025-01-06 | None
206486 | zgcyh_beijing_icyq | 中关村壹号IC-PARK园区 | zgcyh_beijing_icyq | B1F | ch01005 | 01-05 | 192.168.254.5 | 3559 | None | Pass |  |  |  |  | None | 15e66a97-e7d9-4c29-b5a8-5dd52f87e9d8 | 47e005d2d6131791d976d422b2b7536f | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/24%3A0F%3A9B%3A54%3AF3%3AFC/20250106_173120.jpg?AWSAccessKeyId=LTAI5t8MATbKVpTSR8isTpHc&Signature=4kZKAbCxvpKF%2B%2FSO37TTbtAUF2U%3D&Expires=3312955880 | https://bj.bcebos.com/camera-manage/debug/zgcyh_beijing_icyq/projection/01-05/cam_view_20250106173328.jpg | [{"floor": "B1F", "lot": "1198", "cam": "01-05"}, {"floor": "B1F", "lot": "1197", "cam": "01-05"}, {"floor": "B1F", "lot": "1196", "cam": "01-05"}, {"floor": "B1F", "lot": "1195", "cam": "01-05"}, {"floor": "B1F", "lot": "1194", "cam": "01-05"}] | 2025-01-06 17:31:19 | 2025-01-06 | None
206487 | zgcyh_beijing_icyq | 中关村壹号IC-PARK园区 | zgcyh_beijing_icyq | B1F | ch01006 | 01-06 | 192.168.254.6 | 3559 | None | Pass |  |  |  |  | None | 15e66a97-e7d9-4c29-b5a8-5dd52f87e9d8 | a2be7a5e09def33bd4d18ee35c2bff46 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/24%3A0F%3A9B%3A54%3AF3%3AE9/20250106_173123.jpg?AWSAccessKeyId=LTAI5t8MATbKVpTSR8isTpHc&Signature=b541cYQvyNk9D0ocRx9jcah4NSs%3D&Expires=3312955884 | https://bj.bcebos.com/camera-manage/debug/zgcyh_beijing_icyq/projection/01-06/cam_view_20250106173342.jpg | [{"floor": "B1F", "lot": "1193", "cam": "01-06"}, {"floor": "B1F", "lot": "1192", "cam": "01-06"}, {"floor": "B1F", "lot": "1191", "cam": "01-06"}, {"floor": "B1F", "lot": "1190", "cam": "01-06"}, {"floor": "B1F", "lot": "1189", "cam": "01-06"}] | 2025-01-06 17:31:22 | 2025-01-06 | None
206488 | zgcyh_beijing_icyq | 中关村壹号IC-PARK园区 | zgcyh_beijing_icyq | B1F | ch01007 | 01-07 | 192.168.254.7 | 3559 | None | Pass |  |  |  |  | None | 15e66a97-e7d9-4c29-b5a8-5dd52f87e9d8 | 67de9e9f4b41959ec39e20492271efd3 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/24%3A0F%3A9B%3A54%3AF0%3A6F/20250106_173126.jpg?AWSAccessKeyId=LTAI5t8MATbKVpTSR8isTpHc&Signature=3Vsbdb703ct9j9u27mNl4uT6Z2c%3D&Expires=3312955887 | https://bj.bcebos.com/camera-manage/debug/zgcyh_beijing_icyq/projection/01-07/cam_view_20250106173359.jpg | [{"floor": "B1F", "lot": "1406", "cam": "01-07"}, {"floor": "B1F", "lot": "1405", "cam": "01-07"}, {"floor": "B1F", "lot": "1404", "cam": "01-07"}] | 2025-01-06 17:31:25 | 2025-01-06 | None
206489 | zgcyh_beijing_icyq | 中关村壹号IC-PARK园区 | zgcyh_beijing_icyq | B1F | ch01008 | 01-08 | 192.168.254.8 | 3559 | None | Untest | None | None | None | None | None | 15e66a97-e7d9-4c29-b5a8-5dd52f87e9d8 | 4cf86fa2269cfd4c4440bba38bf96466 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/24%3A0F%3A9B%3A54%3AF4%3A08/20250106_173128.jpg?AWSAccessKeyId=LTAI5t8MATbKVpTSR8isTpHc&Signature=sD%2FUFvGBwElkhee5qMkGwN6r1Aw%3D&Expires=3312955888 | https://bj.bcebos.com/camera-manage/debug/zgcyh_beijing_icyq/projection/01-08/cam_view_20250108151443.jpg | [{"floor": "B1F", "lot": "1177", "cam": "01-08"}, {"floor": "B1F", "lot": "1176", "cam": "01-08"}, {"floor": "B1F", "lot": "1175", "cam": "01-08"}, {"floor": "B1F", "lot": "1174", "cam": "01-08"}, {"floor": "B1F", "lot": "1173", "cam": "01-08"}, {"floor": "B1F", "lot": "1172", "cam": "01-08"}, {"floor": "B1F", "lot": "1129", "cam": "01-08"}, {"floor": "B1F", "lot": "1128", "cam": "01-08"}] | 2025-01-06 17:31:28 | 2025-01-06 | None
206490 | zgcyh_beijing_icyq | 中关村壹号IC-PARK园区 | zgcyh_beijing_icyq | B1F | ch01009 | 01-09 | 192.168.254.9 | 3559 | None | Pass |  |  |  |  | None | 15e66a97-e7d9-4c29-b5a8-5dd52f87e9d8 | 237e2e2defcca4b96a47a995f27a17d6 | https://cameramanage.oss-cn-hangzhou.aliyuncs.com/iot-capture/24%3A0F%3A9B%3A54%3AF3%3AD2/20250106_173130.jpg?AWSAccessKeyId=LTAI5t8MATbKVpTSR8isTpHc&Signature=FI6wFdGF2NPydvGtVmHbBCCQ3TI%3D&Expires=3312955891 | https://bj.bcebos.com/camera-manage/debug/zgcyh_beijing_icyq/projection/01-09/cam_view_20250106173511.jpg | [{"floor": "B1F", "lot": "1188", "cam": "01-09"}, {"floor": "B1F", "lot": "1187", "cam": "01-09"}, {"floor": "B1F", "lot": "1186", "cam": "01-09"}, {"floor": "B1F", "lot": "1185", "cam": "01-09"}, {"floor": "B1F", "lot": "1124", "cam": "01-09"}, {"floor": "B1F", "lot": "1123", "cam": "01-09"}, {"floor": "B1F", "lot": "1122", "cam": "01-09"}, {"floor": "B1F", "lot": "1121", "cam": "01-09"}] | 2025-01-06 17:31:29 | 2025-01-06 | None